Brief Plan – the road to Bihar Hackathon 2027

Amity University Patna  •  Summary of the four event briefs  •  Draft 1 (14 Oct 2026)  •  Budget to be discussed later

Goal: "Amity Patna is where Bihar's companies find talent." Four offline events at Amity Patna build up to one main event in April. Each event has a full brief in its own folder; this page is the short version.

# 1. The four events

| Event | Date | What it is | Who and how many |
| --- | --- | --- | --- |
| 1. Amity Patna Hack Day "Spark" | Sat 28 Nov 2026 | 1-day mini hackathon with a "Hackathon 101" workshop; teams build and pitch in 5 hours | Amity Patna students only; 60–70 students, 16–20 teams |
| 2. Patna Solve-a-thon | Sat 16 Jan 2027 | 5½-hour problem-solving sprint on company problems revealed on the day; no coding | 15 Patna colleges approached; 30–32 teams; 5–6 companies |
| 3. Patna Hackathon | Sat 27 Mar 2027 | 12-hour build day (8 AM – 8 PM); working prototypes; hiring desk | Patna colleges; 30–32 teams; top 20 go to the final |
| 4. Bihar Hackathon 2027 (final) | Sat–Sun 24–25 Apr 2027 | 30-hour hackathon; company + faculty judges; interviews and offers | Top 20 from Event 3 + 6 wildcards from any Bihar college; 8–10 companies |

# 2. How we organise each event

| Event | Main preparation steps (deadline) |
| --- | --- |
| 1. Hack Day | Approval and rooms (Fri 23 Oct) • problems and judges (Fri 30 Oct) • registration form (Sun 1 Nov) • workshop, mentors, CV reviewers, volunteers (Fri 20 Nov) • food and certificates (Wed 25 Nov) • dry run (Fri 27 Nov) |
| 2. Solve-a-thon | Approval for outside students + Director's letter (Fri 30 Oct) • college visits on 6 routes (9 Nov – 4 Dec) • 5–6 companies confirmed (Fri 11 Dec) • themes published (Mon 14 Dec) • rooms, gate list, judging sheet (Fri 8 Jan) • dry run (Fri 15 Jan) |
| 3. Patna Hackathon | 6–8 companies (Fri 29 Jan) • approval to end at 10 PM + transport (Fri 5 Feb) • registration opens (Mon 8 Feb) • problems revealed (Mon 22 Feb) • judging and submissions set up (Fri 12 Mar) • food, transport, hiring desk (Fri 19 Mar) • dry run (Fri 26 Mar) |
| 4. Final | Approach 35 companies from November, 8–10 confirmed (Wed 31 Mar) • overnight approval (Fri 29 Jan) • venue (Fri 26 Feb) • finalists and wildcards (29 Mar – 7 Apr) • stay and food (Fri 16 Apr) • hiring desk (Tue 20 Apr) • dry run (Fri 23 Apr) |

# 3. Who manages what

One core team runs all four events; volunteers grow with each event. Fill the Name column once people are confirmed.

| Role | People | What they do across the year | Name |
| --- | --- | --- | --- |
| Faculty convener | 1 | In charge overall; approvals; Director's letters; duty rosters (Events 1–4) |  |
| T&P officer | 1 | Company partners; CV clinic; hiring desk, interviews and offers; campus placements (Events 1–4) |  |
| Technical lead | 1 | Problem statements, workshop, Wi-Fi and power, submissions (Events 1–4) |  |
| Student lead | 1 | Registration, team matching, ambassadors, finalist communication (Events 1–4) |  |
| Relations team | 2–3 | Companies: problems, judges, mentors (Events 2–4) |  |
| Outreach team | 2 faculty + Event 1 volunteers | College visits; 2 student ambassadors per college (Events 2–3) |  |
| Jury head / mentors lead | 1 / 1 | Judging rules (company 60% + faculty 40%), scores, finalist list / mentor rounds and briefings (Events 2–4) |  |
| Marketing | 2 | Posters, class groups, social media, press (Events 1–4) |  |
| Logistics + registration desk | 4–7 | Rooms, food, gate and ID, transport, stay, safety; check-in and calls (Events 1–4) |  |
| Night-duty team | 4–6 faculty + woman warden | Overnight supervision (Event 4) |  |
| Volunteers | 8–10 → 20–25 | Day support; grows from Event 1 to Event 4 |  |

# 4. How each event helps the next

| From → to | What passes on |
| --- | --- |
| Event 1 → Event 2 | ~10 Amity teams; 12–15 volunteers for college visits; first company/alumni partner; registration form and judging sheet |
| Event 2 → Event 3 | Top 10 teams get direct entry; ~20 teams come back; 5–6 companies set problems; 18 ambassadors in 9 colleges |
| Event 3 → Event 4 | Top 20 finalist teams; 6–8 companies likely to recruit; full rehearsal of judging and hiring desk; other teams can apply as wildcards |
| Event 4 → next year | Companies invited to campus placements (3–5 new); results promote next year's events; Bihar Engineering University contact starts the 2027–28 district round |

# 5. Targets for the year (feasible)

Students reached 230–270  •  colleges 10–13  •  companies 8–10  •  interviews 42–55  •  offers 8–12  •  new companies for campus placements 3–5. How each number is worked out is in the Master Plan and the event briefs.

# 6. Decisions needed now

- Approve the four offline events and their dates

- Approve Event 1 (Hack Day, Sat 28 Nov) now – it is six weeks away

- Appoint the faculty convener and confirm the T&P officer's role

- Letters from the Director to Patna college principals (November)

- Budget: to be discussed separately