Master Plan – the road to Bihar Hackathon 2027

Amity University Patna  •  Academic year Aug 2026 – Jun 2027  •  Draft 3 (12 Oct 2026)  •  Budget to be discussed later

# 1. What we are doing

Goal: "Amity Patna is where Bihar's companies find talent." We build up to one main event – Bihar Hackathon 2027 in April – through three smaller events. We start on our own campus, then open to Patna colleges.

- All four events are offline at Amity Patna. Online is used only for registration, idea submission and shortlisting.

- Bihar Hackathon is mainly a Patna event this year. We use the Bihar name from the first edition so the event can grow without a rename. A few wildcard places are open to any college in Bihar.

- Expansion later: in 2027–28 we add colleges from other districts of Bihar.

# 2. The four events

| # | Event | Date | What it is | Who | Feasible size | Folder |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Amity Patna Hack Day "Spark" | Sat 28 Nov 2026 | 1-day mini hackathon with a "Hackathon 101" workshop | Amity Patna students only | 60–70 students, 16–20 teams | 01_Amity_Hack_Day_Nov2026 |
| 2 | Patna Solve-a-thon | Sat 16 Jan 2027 | Problem-solving sprint: company problems revealed on the day, 5½ hours to solve, present to judges (no coding) | All Patna colleges | 8–10 colleges, 30–32 teams on the day | 02_Patna_Solveathon_Jan2027 |
| 3 | Patna Hackathon | Sat 27 Mar 2027 | 12-hour build day (8 AM – 8 PM) | All Patna colleges | 30–32 teams; top 20 go to the final | 03_Patna_Hackathon_Mar2027 |
| 4 | Bihar Hackathon 2027 (FINAL) | Sat–Sun 24–25 Apr 2027 | 30-hour hackathon; company judges; hiring | Top 20 from Event 3 + 6 wildcards | 24–26 teams, 8–10 companies | 04_Final_Bihar_Hackathon_Apr2027 |

Each folder has a brief: what we will do, the event, how it runs, how it helps, the engagement plan, how we counted the numbers, and targets.

# 3. How teams move from event to event

| From | To | How many | Rule |
| --- | --- | --- | --- |
| Event 1 – Hack Day | Event 2 – Patna Solve-a-thon | ~10 Amity teams + 12–15 volunteers | All Hack Day teams invited; volunteers go on college visits |
| Event 2 – Patna Solve-a-thon | Event 3 – Patna Hackathon | 10 teams direct entry; ~20 teams come back | Top 10 skip registration; all others invited first |
| Event 3 – Patna Hackathon | Event 4 – Final | 20 teams | Top 20 by score |
| Wildcard (online shortlist) | Event 4 – Final | 6 teams | Any college in Bihar; 1-page idea due Sun 4 Apr |

# 4. Numbers: earlier draft vs feasible

Earlier drafts used round targets. Amity Patna is a young campus (about 1,200 students; B.Tech intake about 120 a year), and this is our first year running outside events. The feasible numbers below are worked out step by step in each event folder.

| Measure | Earlier draft | Feasible | Why it changed |
| --- | --- | --- | --- |
| Event 1 – students on the day | 100+ | 60–70 | ~400 tech students × 18% register × 70% attend, + a few from other courses |
| Event 2 – colleges / teams on the day | 15+ / 300+ students | 8–10 / 30–32 teams (105–110 students) | 15 colleges approached, ~60% take part, 3–4 teams each; 75% of 42 registered teams come |
| Event 3 – teams on the day | 60–75 | 30–32 | ~40 registered (20 return + 20 new), 80% attend |
| Final – teams | 60–80 (from all Bihar) | 24–26 | Mainly Patna this year: top 20 from March + 6 wildcards, 85% confirm, waitlist fills gaps |
| Final – companies | 15–25 | 8–10 | 35 approached, about 1 in 4 agree |
| Final – interviews | 50+ | 24–30 | 8–10 companies × 3 students |
| Final – offers | 25+ | 6–8 | About 1 in 4 interviews |
| New companies for campus placements | 10+ | 3–5 | About half of companies are new to Amity |

# 5. Year totals (feasible)

| Measure | Total for the year | How we got it |
| --- | --- | --- |
| Different students reached through events | 230–270 | Hack Day ~65 + Solve-a-thon outside students registered ~110 + new Hackathon students ~50 + wildcard applicants ~20 |
| Colleges that take part | 10–13 | Amity + 9 Patna colleges + 1–3 wildcard colleges |
| Companies that take part | 8–10 | Same companies grow: 1 → 5–6 → 6–8 → 8–10 |
| Internship / job interviews | 42–55 | Solve-a-thon 8–10 + Patna Hackathon 10–15 + Final 24–30 |
| Offers | 8–12 | Patna Hackathon 2–4 + Final 6–8 |
| New companies for campus placements | 3–5 | From the final |

# 6. Engagement across the year

The same students and colleges move through the year, so we never start from zero.

| When | Engagement step | Who we engage |
| --- | --- | --- |
| Oct – Nov | Class announcements at Amity; Hack Day; volunteers recruited | Amity Patna students |
| Nov – Dec | College visits with the Director's letter; 1 teacher + 2 student ambassadors per college | 15 Patna colleges |
| Dec – Jan | Solve-a-thon themes and a sample problem published; sprint on campus | Patna students; first companies |
| Feb – Mar | Solve-a-thon teams invited back; Patna Hackathon | Patna students; more companies |
| Apr | Top 20 + wildcards; finalist briefing; the final; hiring desk | Finalists; 8–10 companies |
| May – Jun | Interviews, offers, certificates; companies invited to campus placements | Students; companies; placement cell |

# 7. Month-by-month

| Month | Main work |
| --- | --- |
| Oct 2026 | Approval of this plan • core team with T&P officer • Hack Day registration form • list of 15 Patna colleges and 35 companies |
| Nov 2026 | EVENT 1: Hack Day (Sat 28 Nov) • college visits for Event 2 • first companies for Event 2 |
| Dec 2026 | Exams – online reminders only • Solve-a-thon themes published (Mon 14 Dec) |
| Jan 2027 | EVENT 2: Patna Solve-a-thon (Sat 16 Jan) • Hackathon companies approached |
| Feb 2027 | Patna Hackathon registration (from Mon 8 Feb) and problems (Mon 22 Feb) |
| Mar 2027 | Mid-terms • EVENT 3: Patna Hackathon (Sat 27 Mar) • top 20 invited and wildcard call (Mon 29 Mar) |
| Apr 2027 | Finalists confirm (Sat 3 Apr) • wildcards picked (Wed 7 Apr) • briefing (Sat 10 Apr) • EVENT 4: FINAL (Sat–Sun 24–25 Apr) |
| May – Jun 2027 | Interviews and offers • final report to management • companies invited to campus placements |

# 8. Next year – expanding to Bihar

- Add a Bihar round for colleges in other districts (online shortlist + pitch day at Amity Patna) before the final.

- Grow the number of companies using this year's partners and placement results.

- Keep the same name – Bihar Hackathon 2028 – so the event builds on this year.

# 9. To confirm before announcing

- Amity Patna student numbers by course and year (academic office) – this changes the Event 1 numbers

- Semester, mid-term and end-semester exam dates

- Holi 2027 (assumed about Mon 22 Mar) and Chhath 2026 dates

- Venue seats with power and Wi-Fi (Events 1, 3, 4) and approval for an overnight final

# 10. Decisions needed now

- Approve the four offline events and their dates

- Approve Event 1 (Hack Day, Sat 28 Nov) now – it is six weeks away

- Appoint the faculty convener and confirm the T&P officer's role

- Letters from the Director to Patna college principals (November)

- Budget: to be discussed separately