Event 3 – Patna Hackathon

Event 3 of 4  •  Sat 27 Mar 2027 (after mid-terms)  •  All Patna colleges  •  Amity University Patna  •  Draft 3 (14 Oct 2026)

# 1. What we will do

- Run a 12-hour hackathon where Patna teams build working prototypes for company problems.

- Test the final's judging rules (company 60% + faculty 40%) and the hiring desk.

- Pick the top 20 teams for the final (Bihar Hackathon 2027).

# 2. The event

Patna Hackathon – a 12-hour build day (8 AM – 8 PM, no overnight stay) for teams from Patna colleges. Teams pick one of 6–8 company problems published four weeks earlier, build a working prototype, and are judged by company and faculty judges. The top 20 teams qualify for the Bihar Hackathon 2027 (the final).

| Item | Plan |
| --- | --- |
| Name | Patna Hackathon 2027 |
| Date | Sat 27 Mar 2027, 7:30 AM – 10:00 PM. After mid-terms; the weekend after Holi (about Mon 22 Mar – verify). Fallback: Sat 3 Apr. |
| Who | Teams of 2–4 from Patna colleges; top 10 Event 2 teams get direct entry |
| Problems | 6–8 company problem statements, published Mon 22 Feb |
| Venue | 2–3 labs + main hall (about 150 seats with power) + auditorium for final pitches |
| Format | Offline at Amity Patna. Online is used only for registration – if more than 40 teams register, we shortlist online from a 1-paragraph idea. |
| Feasible size | 40 teams registered, 30–32 teams on the day (110–120 students) |

# 3. How it runs

| Time / step | What happens |
| --- | --- |
| 7:30 | Check-in |
| 8:00 | Hacking starts (12 hours) |
| 11:00 and 15:00 | Mentor rounds with company mentors |
| 13:00 | Lunch |
| 15:00 – 18:00 | Hiring desk open |
| 20:00 | Submissions close (code link + 2-min demo video) |
| 20:00 – 21:00 | Judging at team tables (company 60% + faculty 40%) |
| 21:00 – 21:45 | Top 6 teams pitch on stage |
| 21:45 – 22:00 | Results; top 20 finalists for Event 4 announced; transport for day scholars |

# 4. How we will organise it

The first full build day with outside teams. Main work: companies and problems by February, a venue that works for 12 hours, and late-evening safety and transport. Work to finish before the day, in order.

| By when | Step | Task | Owner |
| --- | --- | --- | --- |
| Fri 29 Jan | Companies | 6–8 companies confirmed (5–6 from Event 2 + 1–2 new), each with a problem, a mentor and a judge | Relations team, T&P officer |
| Fri 5 Feb | Approval and venue | Approval for the event to end at 10 PM with transport; 150 seats with power and Wi-Fi checked | Faculty convener, logistics |
| Mon 8 Feb | Registration | Registration and "find a team" form open; direct-entry letters to top 10 Event 2 teams | Student lead |
| Fri 19 Feb | Problems | Problem statements and 2-min company videos ready for the reveal on Mon 22 Feb | Relations team, technical lead |
| Fri 12 Mar | Judging and submissions | Judging sheet (company 60% + faculty 40%); submission form (code link + 2-min demo video); 6–8 mentors | Jury head, mentors lead |
| Fri 19 Mar | Supplies | Lunch, tea and dinner for ~150; extension boards; Wi-Fi backup; first aid; buses or cabs for day scholars after 10 PM | Logistics |
| Fri 19 Mar | Hiring desk | Room and interview slots for 15:00 – 18:00; CVs of registered students to companies | T&P officer |
| 24 – 26 Mar | Confirm | Call every team; waitlist fills gaps | Registration desk |
| Fri 26 Mar | Dry run | Wi-Fi test with ~120 devices; submission form test; stage and judging table plan | Technical lead, all leads |

# 5. Who manages what

Fill the Name column once people are confirmed. One person can hold two roles in a small event.

| Role | People | What they do | Name |
| --- | --- | --- | --- |
| Faculty convener | 1 | In charge overall; approvals; late-evening duty roster (incl. a woman faculty member till 10 PM) |  |
| T&P officer | 1 | Hiring desk, interviews and offers |  |
| Relations team | 2 | 6–8 companies, problems, company videos, company mentors and judges |  |
| Jury head | 1 | Judging rules, score sheet, top 20 list for the final |  |
| Mentors lead | 1 | Online briefing on 13 Mar; mentor rounds at 11:00 and 15:00 |  |
| Technical lead | 1 | Wi-Fi, power, submission form, tech help desk |  |
| Student lead | 1 | Registration, team finder, ambassadors in each college |  |
| Marketing | 2 | Problem reveal, countdown, results posts |  |
| Logistics | 3 | Food for 3 meals, transport, first aid, late-evening safety |  |
| Registration desk | 2–3 | Check-in and confirmation calls |  |
| Day volunteers | 15–20 | Help desk, food, rooms, time-keeping |  |
| Judges / mentors | 12–16 / 6–8 | 1 company + 1 faculty per problem; company mentors |  |

# 6. How it helps

| For | How it helps |
| --- | --- |
| Students | Build a real prototype for a company; mentors; interviews; a place in the final. |
| The final | Full test of hackathon operations, judging rules and the hiring desk – one month before the final. |
| Companies | See working prototypes, not just ideas; more likely to send recruiters to the final. |
| Management | Proof the team can run a full hackathon with outside colleges. |

## How this event helps the other events

| Event | What this event gives it |
| --- | --- |
| Event 4 – the final | Gives the top 20 finalist teams; full rehearsal of judging, submissions, hiring desk and long-day food and safety; the 6–8 companies are the likely recruiters at the final |
| Wildcards for the final | Teams that miss the top 20 can apply as wildcards with a 1-page idea |
| Companies | 2–4 early offers give us proof to show the companies we approach for the final |

# 7. Engagement plan

## Before, during and after

| Stage | When | What we do | Owner |
| --- | --- | --- | --- |
| Invite back | 18 Jan – 7 Feb | Invite all Event 2 teams; direct-entry letters to top 10; ambassadors restart in each college; open invitation to Patna tech colleges not in Event 2 | Marketing, ambassadors |
| Sign up | 8 Feb – 24 Mar | Registration opens 8 Feb; online "find a team" form; college-wise team count every week | Student lead |
| Problem reveal | 22 Feb | Problem statements + 2-min company videos | Relations team |
| Mid-terms | Early Mar | Light touch only – one reminder a week | Marketing |
| Prepare | 13 – 24 Mar | Online briefing Sat 13 Mar: "How we judge"; registration closes Wed 24 Mar | Mentors lead |
| Confirm | 24 – 26 Mar | Call every team; waitlist fills gaps | Registration desk |
| After | 29 Mar – 3 Apr | Finalist letters; certificates by college; interviews | T&P, logistics |

## Channels

- Event 2 participants (main channel – direct invite)

- Ambassadors and teachers in each Patna college

- Open invitation (Director's letter + social media) to Patna tech colleges not in the Event 2 list: IIT Patna, Government Polytechnic Patna-7, New Government Polytechnic Patna-13, Ganga Devi Mahila College, T.P.S. College, R.K.D. College – teams from these are extra, not counted in section 8

- Instagram and LinkedIn: problem reveal, countdown, results

# 8. How we counted the numbers

Each number comes from a base we can check (students, colleges, companies) multiplied by a realistic rate. Rates are taken from similar events in our research tracker. Fill the "Actual" column after the event.

| Step | Count | How we got it | Actual |
| --- | --- | --- | --- |
| Event 2 teams on the day | ~31 | From Event 2 |  |
| Event 2 teams that register again | ~20 | About 65% come back (they already know the campus and the format) |  |
| New teams from Patna colleges and Amity | ~20 | About 2 new teams from each of the 9 colleges + Amity |  |
| Teams registered | ~40 | 20 + 20 |  |
| Teams on the day | 30–32 | About 80% attend after confirmation calls |  |
| Students on the day | 110–120 | 31 teams × 3.6 |  |
| Seats needed | ~150 | 115 students + ~35 judges, mentors and volunteers – check the venue |  |
| Teams that submit a prototype | 26–28 | About 85% of teams on the day |  |
| Teams that qualify for the final | 20 | About the top 75% of the 26–28 submissions |  |
| Companies | 6–8 | 5–6 from Event 2 + 1–2 new |  |
| Interviews | 10–15 | 6–8 companies × about 2 each |  |
| Offers | 2–4 | About 1 in 4 interviews |  |

# 9. Feasible targets for management

| Measure | Feasible target | Actual |
| --- | --- | --- |
| Teams registered / on the day | 40 / 30–32 |  |
| Students on the day | 110–120 |  |
| Teams submitting a prototype | 26–28 |  |
| Teams qualifying for the final | 20 |  |
| Companies | 6–8 |  |
| Interviews / offers | 10–15 / 2–4 |  |
| Feedback score (out of 5) | 4+ |  |

# 10. To confirm before announcing

- Mid-term dates and Holi 2027 date

- Venue seats with power and Wi-Fi for ~150 people

- Approval for the event to end at 10 PM, with transport

Budget: to be discussed later.