Event 4 – Bihar Hackathon 2027 (the end goal)

Event 4 of 4  •  Sat–Sun 24–25 Apr 2027 (fallback 1–2 May)  •  Mainly Patna colleges; open to any college in Bihar  •  Amity University Patna  •  Draft 3 (14 Oct 2026)

# 1. What we will do

- Bring the best teams of the year to Amity Patna for a 30-hour offline hackathon.

- Companies set the problems, judge with faculty, and interview and hire on the spot.

- Use the name "Bihar Hackathon" from the first edition. This year the teams come mainly from Patna colleges, with a few wildcard places open to any college in Bihar. In later years we expand to colleges across Bihar.

- Invite every company to Amity Patna's campus placements.

# 2. The event

Bihar Hackathon 2027 – Amity Patna's main event: 30 hours of building on real problems from Bihar companies and government departments. Company experts and faculty judge together (company 60%, faculty 40%). Winners get internship and job offers. Purpose: "Amity Patna is where Bihar's companies find talent." First edition: mainly Patna colleges, under a Bihar name so the event can grow without a rename.

| Item | Plan |
| --- | --- |
| Name | Bihar Hackathon 2027 (1st edition) |
| Date | Sat 10:30 AM – Sun 4:30 PM, 24–25 Apr 2027 (30 hours). Fallback: 1–2 May. |
| Format | Offline at Amity Patna. Online only for the wildcard shortlist. |
| Who | Top 20 teams from Event 3 (Patna Hackathon) + 6 wildcard teams from any college in Bihar (+ waitlist) |
| Wildcard (online shortlist) | Open to teams that did not qualify in March or are from outside Patna: 1-page idea due Sun 4 Apr • 6 wildcards announced Wed 7 Apr |
| Problems | 8–10 problem statements from Bihar companies, startups, PSUs and government departments |
| Judging | Per problem statement: 1 company judge + 1 faculty judge; company 60% + faculty 40%; no faculty judges their own college |
| Hiring | Hiring desk Sat 3 PM onwards; offers announced at closing; interviews in the 2 weeks after |
| Feasible size | 24–26 teams (85–95 students), 8–10 companies |

# 3. How it runs

| Time / step | What happens |
| --- | --- |
| Mon 29 Mar | Top 20 Patna Hackathon teams invited; wildcard call opens |
| Sat 3 Apr | Invited teams confirm |
| Sun 4 Apr / Wed 7 Apr | Wildcard ideas due / 6 wildcards announced |
| Sat 24 Apr 8:30 | Check-in |
| Sat 9:30 | Opening with company leaders |
| Sat 10:30 | Hacking starts (30 hours) |
| Sat 15:00 | Company stalls and hiring desk open |
| Sat 17:00 and 23:00 | Mentor rounds; overnight hacking with supervision |
| Sun 9:00 | Final mentor round |
| Sun 16:30 | Submissions close |
| Sun 16:30 – 18:30 | Judging per problem statement |
| Sun 18:30 – 19:30 | Top 8 teams pitch on stage |
| Sun 19:30 | Prizes, offers announced, close |

# 4. How we will organise it

The biggest event: overnight, outside students, 8–10 companies. Approvals and companies take longest, so this work starts in November alongside Events 1–3. Work to finish before the day, in order.

| By when | Step | Task | Owner |
| --- | --- | --- | --- |
| Nov – Wed 31 Mar | Companies | Approach 35 companies (PSU and government letters by December); confirm 8–10, each with a problem and a judge | Relations team, T&P officer |
| Fri 29 Jan | Approvals | Approval for an overnight event with outside students: separate supervised rest areas, woman warden | Faculty convener |
| Fri 26 Feb | Venue | Hall for ~120 overnight with power backup and cooling for April heat; rest areas; interview rooms | Logistics |
| Wed 31 Mar | Problems and judges | 8–10 problem statements; 16–20 judges; prizes fixed | Relations team, jury head |
| 29 Mar – 7 Apr | Finalists and wildcards | Top 20 invited; wildcard call (incl. Bihar Engineering University circular); 6 wildcards picked | Student lead, jury head |
| Sat 10 Apr | Briefing | Finalist briefing: rules, stay, what to bring | Student lead |
| Fri 16 Apr | Stay and food | 5 meals + midnight snack for ~120; bedding; first aid and on-call doctor; night security | Logistics |
| Tue 20 Apr | Hiring desk | CV pack of all finalists sent to companies; interview rooms and slots | T&P officer |
| Thu 22 Apr | Media | Press note (Hindi and English); photographer; certificates and trophies | Marketing |
| Fri 23 Apr | Dry run | Overnight duty roster (faculty in shifts); power backup and Wi-Fi test; stage plan | Faculty convener, all leads |

# 5. Who manages what

Fill the Name column once people are confirmed. One person can hold two roles in a small event.

| Role | People | What they do | Name |
| --- | --- | --- | --- |
| Faculty convener | 1 | In charge overall; approvals; Director's letters; overnight duty roster |  |
| T&P officer | 1 | Hiring desk, CV packs, interviews and offers tracking; invites companies to campus placements |  |
| Relations team | 3 | 35 companies; problems, data and mentors; company guest desk |  |
| Jury head | 1 | Judging rules (no faculty judges their own college), scores, results |  |
| Mentors lead | 1 | Mentor rounds at 17:00, 23:00 and 9:00 |  |
| Technical lead | 1 | Network, power backup, submissions, tech help desk |  |
| Student lead | 1 | Finalist and wildcard communication; briefing |  |
| Marketing / media | 2 | Press, photographer, live updates |  |
| Logistics | 4 | Stay, food, heat, security, medical |  |
| Night-duty team | 4–6 faculty in shifts + woman warden | Supervise the hall and rest areas through the night |  |
| Day volunteers | 20–25 | Welcome desk, food, rooms, company guests |  |
| Judges / mentors | 16–20 / 8–10 | 1 company + 1 faculty per problem; company mentors |  |

# 6. How it helps

| For | How it helps |
| --- | --- |
| Students | Compete in a named state-level event; meet 8–10 employers; internship and job offers. |
| Amity Patna placements | Companies that judge and hire here are invited to our campus placements – the main result for management. |
| Amity Patna's name | The "Bihar Hackathon" name is ours from year one; Patna knows Amity as the host where companies find talent. |
| Next year | A proven format and a name we can expand: add colleges from other districts in 2027–28. |

## How this event helps the other events

| Event | What this event gives it |
| --- | --- |
| Amity Patna placements | Companies that judge and hire here are invited to campus placements; 3–5 new companies expected |
| Next year's Events 1–3 | Results and offers are used to promote next year's Hack Day and to bring back colleges and companies; this year's volunteers become next year's core team |
| Bihar Hackathon 2028 | Wildcard colleges and the Bihar Engineering University contact start the district round planned for 2027–28 |

# 7. Engagement plan

## Before, during and after

| Stage | When | What we do | Owner |
| --- | --- | --- | --- |
| Companies | Nov – Mar | Approach 35 companies from November (PSUs and government need letters early); confirm 8–10 by 31 Mar | Relations, T&P |
| Finalists | 29 Mar – 3 Apr | Finalist letter + confirmation form; waitlist fills any gap | Logistics |
| Wildcards | 29 Mar – 7 Apr | Wildcard call shared through Patna ambassadors, social media and a request to Bihar Engineering University (Mithapur) to circulate it to its engineering colleges across Bihar; 6 teams picked online | Marketing, jury head |
| Prepare | 10 Apr | Finalist briefing on campus (or online): rules, stay, what to bring | Student lead |
| Data | 12 – 20 Apr | Companies share sample data and mentors; finalists can ask questions | Relations |
| On the days | 24 – 25 Apr | Welcome desk, mentors, hiring desk, midnight activity, live updates | All |
| After | 26 Apr – May | Interviews and offers tracked; CV packs; certificates; final report to management | T&P, faculty convener |

## Channels

- Direct contact with each finalist team (letters, WhatsApp, calls)

- Patna college ambassadors and social media for the wildcard call

- Bihar Engineering University circular to its affiliated engineering colleges across Bihar (wildcard call) – one letter reaches colleges outside Patna; it also starts the 2027–28 expansion

- Company leaders and PSUs through official letters from the Director

- Instagram, LinkedIn and Patna newspapers (Hindi and English) for the opening and results

# 8. How we counted the numbers

Each number comes from a base we can check (students, colleges, companies) multiplied by a realistic rate. Rates are taken from similar events in our research tracker. Fill the "Actual" column after the event.

| Step | Count | How we got it | Actual |
| --- | --- | --- | --- |
| Teams from Event 3 (Patna Hackathon) | 20 | About the top 75% of the 26–28 teams that submit in March |  |
| Wildcard ideas received | ~25 | Teams that missed March + a few from outside Patna |  |
| Wildcard teams | 6 | About 1 in 4 wildcard ideas |  |
| Teams invited | 26 | 20 + 6 |  |
| Teams that come | 24–26 | About 85% confirm (22); waitlist teams fill 2–4 places |  |
| Students | 85–95 | 25 teams × 3.6 |  |
| Companies approached (Nov – Mar) | 35 | Alumni employers, Patna IT firms, Bihar startups, PSUs, banks, government |  |
| Companies that take part | 8–10 | About 1 in 4 – includes the 6–8 from Events 2 and 3 |  |
| Judges | 16–20 | 8–10 problems × (1 company + 1 faculty) |  |
| Interviews | 24–30 | 8–10 companies × 3 students each |  |
| Offers (internships / jobs / fast-tracks) | 6–8 | About 1 in 4 interviews |  |
| New companies for campus placements | 3–5 | About half of the companies are new to Amity |  |

# 9. Feasible targets for management

| Measure | Feasible target | Actual |
| --- | --- | --- |
| Finalist teams / students | 24–26 / 85–95 |  |
| Colleges represented | 8–10 |  |
| Companies taking part | 8–10 |  |
| Interviews | 24–30 |  |
| Offers | 6–8 |  |
| New companies coming for campus placements | 3–5 |  |
| Media | 2–3 news stories (Patna papers) |  |
| Feedback – students / companies (out of 5) | 4+ / 4+ |  |

# 10. To confirm before announcing

- End-semester exam dates – the final must finish before them

- Approval for an overnight event with students from other colleges (separate supervised rest areas, woman warden)

- Hall capacity for ~120 people overnight (students + judges + volunteers) with power backup; plan for April heat

Budget: to be discussed later.