End Goal – Bihar-Level Hackathon 2027

Amity University Patna  •  Agreed end goal (budget to be discussed later)  •  12 Oct 2026

# 1. Purpose

Build Amity Patna's name for placements: "Amity Patna is where Bihar's companies find talent."

# 2. The end goal

| Item | Plan |
| --- | --- |
| Event | Bihar-Level Hackathon at Amity Patna |
| When | Sat–Sun 24–25 Apr 2027, within the academic year Aug 2026 – Jun 2027 (fallback: Sat–Sun 1–2 May 2027) |
| Format | 30-hour in-person hackathon for 60–80 finalist teams from across Bihar |
| Problem statements | From 15–25 Bihar companies (e.g. DeHaat, Husk Power, NTPC, IOCL Barauni, Sudha Dairy, SBI) plus government departments |
| Judging | Company experts and faculty together – company 60%, faculty 40% |
| Hiring | Internship and job offers on the spot; companies invited to Amity Patna's campus placements |

# 3. Results that matter most to management

| Measure | Target |
| --- | --- |
| Internship / job interviews | 50+ |
| Offers made | 25+ |
| New companies coming for campus placements | 10+ |

# 4. Next step

- Sub-events that lead to this goal: see 02_Sub_Events_Plan.docx (1. Amity Hack Day 28 Nov → 2. Patna Ideathon 16 Jan → 3. Bihar Online Qualifier 13 Feb – 20 Mar → 4. Patna Hackathon 27 Mar → 5. Final 24–25 Apr).

- Budget: to be discussed later.