Event 2 – Patna Ideathon

Event 2 of 4  •  Sat 16 Jan 2027 (start of 4th semester)  •  All Patna colleges  •  Amity University Patna  •  Draft 2 (12 Oct 2026)

# 1. What we will do

- Open our first event to students of other Patna colleges.

- Get 5–6 companies to give real problem statements and judge – our first company partners.

- Build a contact person (teacher + 2 students) in each participating college.

- Send the best teams forward to the Patna Hackathon in March.

# 2. The event

Patna Ideathon – an idea contest on real company problems. Teams from Patna colleges choose one company problem, send a 3-slide idea online, and the best 24 teams pitch on campus to company and faculty judges. No coding needed, so students of any course can take part. A CV clinic runs on the same day.

| Item | Plan |
| --- | --- |
| Name | Patna Ideathon 2027 |
| Date | Sat 16 Jan 2027, 9:00 AM – 4:00 PM. Early in the 4th semester, before late-January fests (Celesta, Elegante, Virasat). Fallback: Sat 23 Jan. |
| Who | Students of Patna colleges (UG/PG, any course); teams of 2–4 from one college |
| Problems | 5–6 problem statements, one from each partner company |
| Format | Offline pitch day at Amity Patna. Online only for shortlisting: problems published Mon 14 Dec • 3-slide ideas due Tue 12 Jan • 24 teams shortlisted Wed 13 Jan |
| Venue | Auditorium + 3 pitch rooms + 2 rooms for CV clinic |
| Feasible size | 8–10 colleges, 160–180 registered, 32–38 ideas, 24 teams pitch, 110–130 people on campus |

# 3. How it runs

| Time / step | What happens |
| --- | --- |
| 9:00 | Check-in |
| 9:30 | Opening: each company explains its problem (3 min each) |
| 10:15 – 12:30 | Pitches in 3 rooms, 8 teams per room (5 min + 3 min Q&A); CV clinic open for all |
| 12:30 | Lunch and networking with companies |
| 13:30 – 14:30 | Top 6 teams pitch on stage |
| 14:30 | Talk: "What Bihar companies look for in freshers" |
| 15:15 – 16:00 | Results; top 10 students get interview slots; top 10 teams get direct entry to Event 3; Patna Hackathon announced |

# 4. How it helps

| For | How it helps |
| --- | --- |
| Students | Pitch to real companies, CV review, chance of internship interviews, direct entry to the hackathon. |
| Reaching Patna | First contact person in each participating college – reused for Events 3 and 4. |
| Companies | First 5–6 company partners; they test the problem-statement template used at the final. |
| Organising team | First event with outside students and company judges – tests the judging panel (company + faculty). |
| Management | Proof that other colleges and companies come to Amity Patna. |

# 5. Engagement plan

## Before, during and after

| Stage | When | What we do | Owner |
| --- | --- | --- | --- |
| List and letter | 19 Oct – 6 Nov | Contact sheet of 15 Patna colleges; Director's letter to each principal | Faculty convener |
| Visit | 9 Nov – 4 Dec | Visit each college with 2 Event 1 volunteers; name 1 teacher + 2 student ambassadors per college | Outreach team |
| Sign up | 30 Nov – 10 Jan | Registration opens; problems published 14 Dec; weekly college-wise count shared with ambassadors | Marketing |
| Exams / break | Dec | End-semester exams – only reminders; idea template and a 10-min "how to write 3 slides" video | Technical lead |
| Push | 4 – 12 Jan | Semester starts: class announcements in each college; ideas due 12 Jan | Ambassadors |
| Confirm | 13 – 15 Jan | Shortlist announced; call every shortlisted team | Registration desk |
| After | 18 – 25 Jan | Certificates by college; interview slots; all teams invited to Event 3; results sheet | T&P, student lead |

## Channels

- College visits with the Director's letter (main channel)

- Student ambassadors in class WhatsApp groups (2 per college)

- Teacher announcements in each college

- Instagram and LinkedIn: problem reveal (14 Dec), countdown, results

- Event 1 participants for Amity Patna teams

# 6. How we counted the numbers

Each number comes from a base we can check (students, colleges, companies) multiplied by a realistic rate. Rates are taken from similar events in our research tracker. Fill the "Actual" column after the event.

| Step | Count | How we got it | Actual |
| --- | --- | --- | --- |
| Patna colleges we approach | 15 | List: NIT Patna, BIT Patna, NSIT Bihta, Patna Science College, Patna Women's College, Magadh Mahila, A.N. College, St. Xavier's (Patna), J.D. Women's, College of Commerce, CIMP, NIFT Patna, Maulana Azad College of Engg., B.N. College, Patna College |  |
| Colleges that take part | 9 | About 60% of approached colleges respond and send teams in a first edition |  |
| Teams per outside college | 3 | A first-time outside event usually gets 2–4 teams per college |  |
| Outside teams submitting ideas | ~27 | 9 × 3 |  |
| Amity Patna teams submitting ideas | ~8 | About half of the 16–20 Event 1 teams continue |  |
| Total ideas submitted | 32–38 | 27 + 8 = 35 |  |
| Teams registered | ~50 | About 70% of registered teams actually submit → 35 ÷ 0.7 |  |
| Students registered | 160–180 | 50 teams × 3.4 students |  |
| Teams pitching on campus | 24 | 3 rooms × 8 teams (8 min each ≈ 65 min per room) – a room limit |  |
| People on campus | 110–130 | 24 teams (~80 students) + 30–40 CV-clinic visitors + 10–15 guests |  |
| Companies with a problem statement | 5–6 | Approach 25 companies; about 1 in 4 agrees for a first event |  |
| Internship interviews | 8–10 | Top 10 students; companies agree to interview them |  |
| Ambassadors in place | 18 | 9 colleges × 2 |  |

# 7. Feasible targets for management

| Measure | Feasible target | Actual |
| --- | --- | --- |
| Patna colleges that take part | 8–10 |  |
| Students registered / ideas submitted | 160–180 / 32–38 |  |
| Teams pitching on campus | 24 |  |
| People on campus | 110–130 |  |
| Companies with a problem statement | 5–6 |  |
| Internship interviews | 8–10 |  |
| Ambassadors in place for Events 3–4 | 18 |  |
| Feedback score (out of 5) | 4+ |  |

# 8. To confirm before announcing

- 4th-semester start date at Amity Patna and the main Patna colleges

- 2027 dates of Celesta, Elegante and Virasat

- Names and contacts of the 15 colleges

- Approval for students from other colleges on campus

Budget: to be discussed later.