Sub-event 1 – Amity Patna Hack Day "Spark"

Event brief  •  Amity University Patna – Amity students only  •  Sat 28 Nov 2026  •  Draft 1 (12 Oct 2026)

# 1. What the event is

Amity Patna Hack Day "Spark" is a one-day mini hackathon for Amity Patna students only. Teams learn how a hackathon works in the morning, then build a simple solution to a real problem in the afternoon and pitch it to faculty and a company judge. It is the final event in miniature: the same format and rules, at a small scale, on our own campus.

| Item | Plan |
| --- | --- |
| Name | Amity Patna Hack Day "Spark" (the first spark before the Patna and Bihar events) |
| Date | Sat 28 Nov 2026, 9:00 AM – 5:30 PM (fallback: Sat 21 Nov 2026 – both dates stay in November). Comes after Diwali (8 Nov) and Chhath. |
| Who | All Amity Patna students, any year or course; teams of 2–4. Beginners welcome. |
| Scale | 100+ students (25–30 teams) |
| Problem statements | 4–5 short problems: 2–3 from campus life (e.g. attendance, canteen queue, placement updates) and 1–2 from a local company or startup |
| Venue | Amity Patna – 2 labs, seminar hall, 2 rooms (mentors, CV clinic) |

# 2. How the day runs

| Time | What happens |
| --- | --- |
| 9:00 | Check-in, teams formed (solo students matched into teams) |
| 9:30 – 10:30 | "Hackathon 101" workshop: how to read a problem, build a quick prototype (no-code/AI tools allowed), and pitch in 3 minutes |
| 10:30 | Problem statements revealed – teams choose one |
| 10:45 – 15:45 | Build time (5 hours) • mentor round at 12:30 • lunch 13:00 • CV clinic open for everyone from 13:30 |
| 15:45 – 16:45 | Pitches: 3 min + 2 min Q&A per team, in 2 rooms |
| 16:45 – 17:30 | Results, certificates, top teams announced; Patna Ideathon (16 Jan) announced |

Judging uses a short version of the final's rubric (problem, idea, working demo, feasibility, pitch) with 1 company or alumni judge + 1 faculty judge per room.

# 3. How it helps reach the end goal

| For | How it helps |
| --- | --- |
| Amity students | A first hackathon in a safe, familiar setting. They learn team work, fast building and pitching, get a CV review, and become stronger teams for the Patna events and the final. |
| Our organising team | A low-risk practice run of everything the final needs: registration, problem statements, judging rules, timing, volunteers. Mistakes are found now, not in April. |
| Reaching other colleges | Hack Day participants become the volunteers and student ambassadors who visit other Patna colleges for the January Ideathon. |
| Companies | 1–2 local companies try the format at a small scale – likely partners for January. |
| Placements | The T&P officer is involved from day one; CVs are collected; companies meet Amity students first. |
| Management | The first proof: students come, the team delivers, companies take part. The results sheet supports approval of the Patna Ideathon with outside students. |

# 4. Results we will report

| Measure | Target |
| --- | --- |
| Registrations / students who attend | 120+ / 100+ |
| Teams that pitch a working demo or prototype | 20+ |
| Departments represented | 4+ |
| Company / alumni judges | 1–2 companies + 2–3 alumni |
| CVs reviewed | 60+ |
| Volunteers and ambassadors signed up for the Patna events | 20+ |
| Feedback score (out of 5) | 4+ |

# 5. Where it fits

- 1. Amity Patna Hack Day "Spark" (Sat 28 Nov 2026) – Amity students only

- 2. Patna Ideathon (Sat 16 Jan 2027) – all Patna colleges

- 3. Bihar Online Qualifier (13 Feb – 20 Mar 2027) – colleges across Bihar

- 4. Patna Hackathon (Sat 27 Mar 2027) – all Patna colleges

- 5. FINAL – Bihar-Level Hackathon (Sat–Sun 24–25 Apr 2027)

Verify: Amity Patna odd-semester exam dates (the event must come before them) and the Chhath date. Budget to be discussed later.