Event 3 – Bihar Ideathon (pitch day at Amity Patna)

Event 3 of 5  •  Pitch day Sat 20 Mar 2027 (online shortlist before it)  •  Colleges across Bihar outside Patna  •  Amity University Patna  •  Draft 2 (12 Oct 2026)

# 1. What we will do

- Open the series to colleges across Bihar outside Patna.

- Shortlist teams online from their 5-slide ideas, then invite the best 30 teams to pitch in person at Amity Patna.

- Pick the teams from outside Patna who go to the final.

# 2. The event

Bihar Ideathon – teams from colleges outside Patna pick one company problem statement and send a 5-slide idea online. Faculty and companies shortlist the best 30 teams, who come to Amity Patna for a one-day pitch day (offline). The top 14–15 teams qualify for the Bihar-Level Hackathon in April. (Patna teams qualify through Event 4.)

| Item | Plan |
| --- | --- |
| Name | Bihar Ideathon 2027 |
| Format | Offline pitch day at Amity Patna. Online is used only for registration, idea submission and shortlisting. |
| Dates | Registration and problems out Sat 13 Feb • ideas due Sun 7 Mar, 11:59 PM • shortlist of 30 teams announced Fri 12 Mar • pitch day Sat 20 Mar at Amity Patna |
| Who | Students of colleges in Bihar outside Patna district; teams of 2–4 |
| What teams send (online) | 5 slides: problem, solution, technology, impact, team (+ optional 2-min video) |
| Shortlisting (online) | 2 faculty score each idea (out of 40); each company checks the ideas for its own problem; max 3 shortlisted teams per college |
| Pitch day timing | 10:00 – 16:00, so teams can travel by morning trains/buses and return the same evening |
| Feasible size | 250–300 registered, 45–55 ideas, 30 teams invited, 22 teams pitch, 14–15 finalists |

# 3. How it runs

| Time / step | What happens |
| --- | --- |
| Sat 13 Feb | Registration opens; problem statements published |
| Sat 20 Feb, Sat 27 Feb | Optional online help sessions: how to read a company problem; how to make a 5-slide idea |
| Sun 7 Mar | Ideas due (online) |
| 8 – 11 Mar | Online shortlisting by faculty and companies |
| Fri 12 Mar | 30 teams invited to the pitch day; travel details sent; 5 waitlist teams |
| Sat 20 Mar 10:00 | Check-in at Amity Patna |
| 10:30 – 13:30 | Opening; pitches in 3 rooms, 10 teams per room (5 min + 3 min Q&A) |
| 13:30 | Lunch; teams meet companies |
| 14:30 – 15:30 | Top 6 pitch on stage |
| 15:30 – 16:00 | Finalists announced (14–15 teams); close in time for evening trains |

# 4. How it helps

| For | How it helps |
| --- | --- |
| Students outside Patna | A real stage to pitch to companies; a place in a statewide final. |
| The final | Makes the final truly Bihar-level – finalists from 7–9 districts, chosen after seeing them in person. |
| Companies | More teams working on their problems; first look at talent from across Bihar. |
| Management | Colleges from other districts visit Amity Patna – statewide reach. |

# 5. Engagement plan

## Before, during and after

| Stage | When | What we do | Owner |
| --- | --- | --- | --- |
| Find colleges | 4 – 22 Jan | List of 40 colleges outside Patna with tech courses; email + call to each principal and HoD | Outreach team |
| Ambassadors | 11 Jan – 12 Feb | Recruit 30 ambassadors in about 20 colleges (LinkedIn, coding clubs, Event 2 contacts); WhatsApp group and poster kit | Outreach team |
| Sign up | 13 Feb – 7 Mar | Registration; 2 help sessions; weekly district count; reminders 7, 3 and 1 day before the deadline | Marketing, ambassadors |
| Shortlist | 12 Mar | Call every shortlisted team; share travel routes, timing and a contact person; ambassadors help teams travel together | Logistics |
| Pitch day | 20 Mar | Welcome desk, lunch, meet the companies, certificates for all who pitch | All |
| After | 22 Mar – 3 Apr | Finalists confirm by 3 Apr; non-finalists get certificates and a thank-you note | Logistics |

## Channels

- Student ambassadors in each college (main channel)

- Emails and calls to principals and HoDs

- Unstop / Devfolio listing for registration and submission

- Instagram and LinkedIn, with Hindi posters for district colleges

# 6. How we counted the numbers

Each number comes from a base we can check (students, colleges, companies) multiplied by a realistic rate. Rates are taken from similar events in our research tracker. Fill the "Actual" column after the event.

| Step | Count | How we got it | Actual |
| --- | --- | --- | --- |
| Colleges outside Patna we contact | 40 | Engineering colleges (Bihar has a government engineering college in most districts) + colleges with BCA – make the list from BEU and AKU websites |  |
| Colleges with an active ambassador | 20 | About half of contacted colleges give us a student contact |  |
| Students registered | 250–300 | ~12 per active college (240) + ~40 from other colleges. Check: Bihar Police EOU Cyber Hackathon got 302 applications statewide |  |
| Teams registered | ~80 | 280 ÷ 3.5 |  |
| Ideas submitted (online) | 45–55 | About 60–65% of registered teams submit |  |
| Teams invited to the pitch day | 30 | 3 rooms × 10 teams (8 min each ≈ 80 min per room) – a room limit |  |
| Teams that travel and pitch | ~22 | About 75% – some teams cannot travel or have exams |  |
| Students on campus | ~80 | 22 teams × 3.6 |  |
| Finalist teams | 14–15 | About the top two-thirds of teams who pitch |  |
| Districts with a finalist | 7–9 | Max 3 shortlisted teams per college spreads them out |  |
| Screening faculty needed | 10 | 50 ideas × 2 faculty = 100 scorings ÷ 10 = 10 each |  |

# 7. Feasible targets for management

| Measure | Feasible target | Actual |
| --- | --- | --- |
| Colleges with registrations | 20+ |  |
| Students registered / ideas submitted | 250–300 / 45–55 |  |
| Teams pitching at Amity Patna | ~22 (30 invited) |  |
| Finalist teams (+ waitlist) | 14–15 (+5) |  |
| Districts with registrations / finalists | 12+ / 7–9 |  |
| Ambassadors active | 30 |  |
| Feedback score (out of 5) | 4+ |  |

# 8. To confirm before announcing

- List of colleges outside Patna with tech courses (BEU / AKU websites)

- Mid-term dates – the idea deadline (7 Mar) and pitch day (20 Mar) should not fall in exam weeks

- Travel support for outside teams – to be decided with the budget

- Two events on back-to-back Saturdays (20 and 27 Mar) – make sure the team and volunteers can cover both

Budget: to be discussed later.