Event 1 – Amity Patna Hack Day "Spark"

Event 1 of 4  •  Sat 28 Nov 2026 (fallback Sat 21 Nov)  •  Amity Patna students only  •  Amity University Patna  •  Draft 2 (12 Oct 2026)

# 1. What we will do

- Run a one-day mini hackathon only for Amity Patna students – our first event, on our own campus.

- Teach students how a hackathon works, then let teams build a simple solution and pitch it.

- Use the day as a practice run of the format we will use for the Patna and Bihar events.

- Sign up Amity students as volunteers and ambassadors for the January event.

# 2. The event

Amity Patna Hack Day "Spark" – "the first spark" before the Patna and Bihar events. In the morning, students attend a short "Hackathon 101" workshop. Then teams of 2–4 pick one real problem (from campus life or a local company), build a simple solution in 5 hours, and pitch it to faculty and a company/alumni judge.

| Item | Plan |
| --- | --- |
| Name | Amity Patna Hack Day "Spark" |
| Date | Sat 28 Nov 2026, 9:00 AM – 5:30 PM (fallback: Sat 21 Nov 2026). After Diwali (8 Nov) and Chhath. |
| Who | All Amity Patna students, any course and year; teams of 2–4; beginners welcome; solo students matched into teams on the day |
| Problems | 4 problem statements: 3 from campus life (e.g. attendance, canteen queue, placement notices) + 1 from a local company or alumni |
| Format | Offline on campus; registration by Google Form (no shortlisting – everyone who registers can come, up to the seat limit) |
| Venue | 2 computer labs + seminar hall + 1 room for CV clinic (about 90 seats – confirm) |
| Feasible size | 60–70 students on the day, 16–20 teams (see section 6) |

# 3. How it runs

| Time / step | What happens |
| --- | --- |
| 2 Nov – 25 Nov | Registration open (Google Form, with CV upload) |
| 9:00 | Check-in; solo students matched into teams |
| 9:30 – 10:30 | "Hackathon 101" workshop: reading a problem, building a quick prototype (no-code and AI tools allowed), pitching in 3 minutes |
| 10:30 | Problem statements revealed; teams choose one |
| 10:45 – 15:45 | Build time (5 hours) • mentor round 12:30 • lunch 13:00 • CV clinic 13:30 – 16:30 |
| 15:45 – 16:45 | Pitches in 2 rooms: 3 min + 2 min Q&A per team |
| 16:45 – 17:30 | Results and certificates; volunteer sign-up for January; Patna Solve-a-thon announced |

# 4. How it helps

| For | How it helps |
| --- | --- |
| Amity students | First hackathon in a familiar place; learn to build and pitch; CV review. They become stronger teams for Events 2, 3 and 4. |
| Organising team | Practice run of registration, problem statements, judging, timing and volunteers – problems found in November, not in April. |
| Reaching other colleges | Participants become the volunteers and ambassadors who visit other Patna colleges for Event 2. |
| Companies | 1 local company or alumni employer tries the format; likely partner for January. |
| Management | First proof that students come and the team delivers – supports approval for Event 2 with outside students. |

# 5. Engagement plan

## Before, during and after

| Stage | When | What we do | Owner |
| --- | --- | --- | --- |
| Announce | 2 – 8 Nov | Faculty announce in every tech class; poster in labs, canteen, hostels; class WhatsApp groups | Faculty convener, marketing |
| Sign up | 2 – 25 Nov | Registration form; "no team? we will match you"; daily count shared in class groups; reminder after Chhath | Student lead |
| Warm-up | 16 – 25 Nov | One 30-min online session "What happens at a hackathon"; problem themes shared (not the full statements) | Technical lead |
| Confirm | 26 – 27 Nov | WhatsApp + call to every registered student; waitlist fills gaps | Registration desk |
| On the day | 28 Nov | Workshop, mentors, CV clinic, certificates for all; photo wall | All |
| After | 30 Nov – 7 Dec | Certificates and photos shared; volunteers onboarded for Event 2; results sheet to management | Student lead, faculty convener |

## Channels

- Class announcements by faculty (main channel – reaches every tech student)

- Class and hostel WhatsApp groups

- Posters in labs, canteen, hostels, library

- Amity Patna Instagram: 1 announcement reel + 1 results post

# 6. How we counted the numbers

Each number comes from a base we can check (students, colleges, companies) multiplied by a realistic rate. Rates are taken from similar events in our research tracker. Fill the "Actual" column after the event.

| Step | Count | How we got it | Actual |
| --- | --- | --- | --- |
| Amity Patna students (all courses) | ~1,200 | CollegeDekho lists about 1,200 students – confirm with the academic office |  |
| Students in tech courses (B.Tech, BCA, MCA, BSc IT – all years) | ~400 | Estimate: B.Tech sanctioned intake ~120 a year (NIRF 2025), actual batches smaller + BCA/MCA. Confirm course-wise numbers |  |
| Students from other courses | ~800 | 1,200 – 400 |  |
| Registrations from tech courses | ~70 | 18% of 400 – a first internal hackathon usually draws 15–20% of tech students |  |
| Registrations from other courses | ~25 | 3% of 800 – mainly for mixed teams (design, business, pitch) |  |
| Total registrations | ~95 | 70 + 25 |  |
| Students who attend | 60–70 | 65–75% of registrations attend a free one-day event |  |
| Teams | 16–20 | 65 students ÷ 3.5 per team |  |
| Teams that show a working demo | 13–16 | About 80% of teams finish something to show |  |
| CV reviews possible | 48 | 4 reviewers × 3 hours × 4 CVs per hour – this is the limit |  |
| Volunteers / ambassadors for Event 2 | 12–15 | About 1 in 5 attendees sign up |  |

# 7. Feasible targets for management

| Measure | Feasible target | Actual |
| --- | --- | --- |
| Registrations | 90–100 |  |
| Students who attend | 60–70 |  |
| Teams / teams with a working demo | 16–20 / 13–16 |  |
| Departments represented | 4+ |  |
| Company or alumni judges | 1 company + 2 alumni |  |
| CVs reviewed | 40–48 |  |
| Volunteers signed up for Event 2 | 12–15 |  |
| Feedback score (out of 5) | 4+ |  |

# 8. To confirm before announcing

- Exact student numbers by course and year (academic office) – update section 6

- Odd-semester exam dates – the event must come before them

- Lab and hall seats with working computers and power points

- Chhath 2026 date (assumed mid-November)

Budget: to be discussed later.