Event 2 – Patna Solve-a-thon

Event 2 of 4  •  Sat 16 Jan 2027 (start of 4th semester)  •  All Patna colleges  •  Amity University Patna  •  Draft 2 (12 Oct 2026)

# 1. What we will do

- Open our first event to students of other Patna colleges.

- Give teams a real company problem on the day and 5½ hours to work out a solution – a problem-solving sprint, no coding needed.

- Get 5–6 companies to set the problems and judge – our first company partners.

- Build a contact person (teacher + 2 students) in each participating college, and send the best teams to the Patna Hackathon in March.

# 2. The event

Patna Solve-a-thon – a one-day problem-solving sprint. In the morning, companies reveal their problems. Teams of 2–4 pick one and work on it until the afternoon: understand the problem, find the real cause, design a solution, draw the user flow and screens (on paper or Figma), and plan how it would be built. Then they present to company and faculty judges. Nothing is prepared in advance, so it tests thinking, not preparation. It is the warm-up for the March hackathon, where teams build the real thing.

| Item | Plan |
| --- | --- |
| Name | Patna Solve-a-thon 2027 |
| Date | Sat 16 Jan 2027, 8:00 AM – 5:15 PM (ends before dark). Early in the 4th semester, before late-January fests (Celesta, Elegante, Virasat). Fallback: Sat 23 Jan. |
| Format | Offline at Amity Patna. Online only for registration and, if more than 36 teams register, a 15-minute online logic quiz to shortlist teams. |
| Who | Students of Patna colleges (UG/PG, any course); teams of 2–4 from one college; mixed skills encouraged (tech + business + design) |
| Problems | 5–6 problems, one from each partner company; revealed on the day; max 6 teams per problem. Only the themes (e.g. agriculture, health, local business) are shared in advance. |
| What teams present | 5 slides: the problem and its cause, the solution, user flow + screen sketches, how it would be built, impact and cost |
| Venue | Main hall (sprint), auditorium (opening and final round), 3 rooms for presentations |
| Feasible size | 8–10 colleges, ~42 teams registered, 30–32 teams on the day (105–110 students) |

# 3. How it runs

| Time / step | What happens |
| --- | --- |
| 8:00 | Check-in |
| 8:45 | Opening; each company presents its problem (3 min each) |
| 9:05 | Teams choose a problem (max 6 teams per problem, in order of check-in) |
| 9:15 – 14:45 | Sprint (5½ hours) • mentor round 1 at 10:45 • lunch at desks 12:30 • mentor round 2 at 13:15 |
| 14:45 | Slides submitted |
| 15:00 – 16:15 | Presentations in 3 rooms, 10–11 teams each (4 min + 3 min Q&A); 1 company + 1 faculty judge per room |
| 16:15 – 16:45 | Top 5 teams present on stage |
| 16:45 – 17:15 | Results; top 10 students get interview slots; top 10 teams get direct entry to Event 3; Patna Hackathon announced |

# 4. How it helps

| For | How it helps |
| --- | --- |
| Students | Practise the exact skill a hackathon needs – breaking down a real company problem under time pressure – before having to code it. Chance of internship interviews and direct entry to March. |
| Reaching Patna | First contact person in each participating college – reused for Events 3 and 4. |
| Companies | Easy first step: give one problem and judge for half a day. They see how students think – our first 5–6 company partners. |
| Organising team | First event with outside students and company judges; tests the judging panel (company 60% + faculty 40%) used at the final. |
| Management | Proof that other colleges and companies come to Amity Patna. |

# 5. Engagement plan

## Before, during and after

| Stage | When | What we do | Owner |
| --- | --- | --- | --- |
| List and letter | 19 Oct – 6 Nov | Contact sheet of 15 Patna colleges; Director's letter to each principal | Faculty convener |
| Visit | 9 Nov – 4 Dec | Visit each college with 2 Event 1 volunteers; run a 15-min "how to crack a problem" demo in class; name 1 teacher + 2 student ambassadors | Outreach team |
| Sign up | 30 Nov – 10 Jan | Registration opens; themes published Mon 14 Dec; a sample problem with a worked solution shared; weekly college-wise count | Marketing |
| Exams / break | Dec | End-semester exams – only reminders | Marketing |
| Push | 4 – 10 Jan | Semester starts: class announcements in each college; registration closes Sun 10 Jan | Ambassadors |
| Confirm | 11 – 15 Jan | Logic quiz only if more than 36 teams (Tue 12 Jan); confirmed list Wed 13 Jan; call every team | Registration desk |
| After | 18 – 25 Jan | Certificates by college; interview slots; all teams invited to Event 3; results sheet | T&P, student lead |

## Channels

- College visits with the Director's letter and a short class demo (main channel)

- Student ambassadors in class WhatsApp groups (2 per college)

- Teacher announcements in each college

- Instagram and LinkedIn: themes reveal (14 Dec), sample problem, countdown, results

- Event 1 participants for Amity Patna teams

# 6. How we counted the numbers

Each number comes from a base we can check (students, colleges, companies) multiplied by a realistic rate. Rates are taken from similar events in our research tracker. Fill the "Actual" column after the event.

| Step | Count | How we got it | Actual |
| --- | --- | --- | --- |
| Patna colleges we approach | 15 | List: NIT Patna, BIT Patna, NSIT Bihta, Patna Science College, Patna Women's College, Magadh Mahila, A.N. College, St. Xavier's (Patna), J.D. Women's, College of Commerce, CIMP, NIFT Patna, Maulana Azad College of Engg., B.N. College, Patna College |  |
| Colleges that take part | 9 | About 60% of approached colleges send teams in a first edition |  |
| Teams registered per outside college | 3–4 | A first-time outside event usually gets 2–4 teams per college |  |
| Outside teams registered | ~32 | 9 × 3.5 |  |
| Amity Patna teams registered | ~10 | About half of the 16–20 Event 1 teams |  |
| Total teams registered | ~42 | 32 + 10 (≈145 students) |  |
| Teams on the day | 30–32 | About 75% of registered teams come for a full day |  |
| Students on the day | 105–110 | 31 teams × 3.4 |  |
| Seat and room limit | 36 teams | 3 rooms × 12 teams (7 min each ≈ 85 min per room); main hall ~130 seats – quiz shortlist only if more than 36 register |  |
| Companies with a problem | 5–6 | Approach 25 companies; about 1 in 4 agrees for a first event |  |
| Judges and mentors | 8–10 | 3 rooms × (1 company + 1 faculty) + 2–4 mentors |  |
| Internship interviews | 8–10 | Top 10 students; companies agree to interview them |  |
| Ambassadors in place | 18 | 9 colleges × 2 |  |

# 7. Feasible targets for management

| Measure | Feasible target | Actual |
| --- | --- | --- |
| Patna colleges that take part | 8–10 |  |
| Teams registered / on the day | ~42 / 30–32 |  |
| Students on the day | 105–110 |  |
| Companies with a problem | 5–6 |  |
| Teams presenting a complete solution | 27+ (about 85%) |  |
| Internship interviews | 8–10 |  |
| Ambassadors in place for Events 3–4 | 18 |  |
| Feedback score (out of 5) | 4+ |  |

# 8. To confirm before announcing

- 4th-semester start date at Amity Patna and the main Patna colleges

- 2027 dates of Celesta, Elegante and Virasat

- Names and contacts of the 15 colleges

- Approval for students from other colleges on campus

Budget: to be discussed later.