Event 3 – Patna Hackathon

Event 3 of 4  •  Sat 27 Mar 2027 (after mid-terms)  •  All Patna colleges  •  Amity University Patna  •  Draft 2 (12 Oct 2026)

# 1. What we will do

- Run a 12-hour hackathon where Patna teams build working prototypes for company problems.

- Test the final's judging rules (company 60% + faculty 40%) and the hiring desk.

- Pick the top 20 teams for the final (Bihar Hackathon 2027).

# 2. The event

Patna Hackathon – a 12-hour build day (8 AM – 8 PM, no overnight stay) for teams from Patna colleges. Teams pick one of 6–8 company problems published four weeks earlier, build a working prototype, and are judged by company and faculty judges. The top 20 teams qualify for the Bihar Hackathon 2027 (the final).

| Item | Plan |
| --- | --- |
| Name | Patna Hackathon 2027 |
| Date | Sat 27 Mar 2027, 7:30 AM – 10:00 PM. After mid-terms; the weekend after Holi (about Mon 22 Mar – verify). Fallback: Sat 3 Apr. |
| Who | Teams of 2–4 from Patna colleges; top 10 Event 2 teams get direct entry |
| Problems | 6–8 company problem statements, published Mon 22 Feb |
| Venue | 2–3 labs + main hall (about 150 seats with power) + auditorium for final pitches |
| Format | Offline at Amity Patna. Online is used only for registration – if more than 40 teams register, we shortlist online from a 1-paragraph idea. |
| Feasible size | 40 teams registered, 30–32 teams on the day (110–120 students) |

# 3. How it runs

| Time / step | What happens |
| --- | --- |
| 7:30 | Check-in |
| 8:00 | Hacking starts (12 hours) |
| 11:00 and 15:00 | Mentor rounds with company mentors |
| 13:00 | Lunch |
| 15:00 – 18:00 | Hiring desk open |
| 20:00 | Submissions close (code link + 2-min demo video) |
| 20:00 – 21:00 | Judging at team tables (company 60% + faculty 40%) |
| 21:00 – 21:45 | Top 6 teams pitch on stage |
| 21:45 – 22:00 | Results; top 20 finalists for Event 4 announced; transport for day scholars |

# 4. How it helps

| For | How it helps |
| --- | --- |
| Students | Build a real prototype for a company; mentors; interviews; a place in the final. |
| The final | Full test of hackathon operations, judging rules and the hiring desk – one month before the final. |
| Companies | See working prototypes, not just ideas; more likely to send recruiters to the final. |
| Management | Proof the team can run a full hackathon with outside colleges. |

# 5. Engagement plan

## Before, during and after

| Stage | When | What we do | Owner |
| --- | --- | --- | --- |
| Invite back | 18 Jan – 7 Feb | Invite all Event 2 teams; direct-entry letters to top 10; ambassadors restart in each college | Marketing, ambassadors |
| Sign up | 8 Feb – 24 Mar | Registration opens 8 Feb; online "find a team" form; college-wise team count every week | Student lead |
| Problem reveal | 22 Feb | Problem statements + 2-min company videos | Relations team |
| Mid-terms | Early Mar | Light touch only – one reminder a week | Marketing |
| Prepare | 13 – 24 Mar | Online briefing Sat 13 Mar: "How we judge"; registration closes Wed 24 Mar | Mentors lead |
| Confirm | 24 – 26 Mar | Call every team; waitlist fills gaps | Registration desk |
| After | 29 Mar – 3 Apr | Finalist letters; certificates by college; interviews | T&P, logistics |

## Channels

- Event 2 participants (main channel – direct invite)

- Ambassadors and teachers in each Patna college

- Instagram and LinkedIn: problem reveal, countdown, results

# 6. How we counted the numbers

Each number comes from a base we can check (students, colleges, companies) multiplied by a realistic rate. Rates are taken from similar events in our research tracker. Fill the "Actual" column after the event.

| Step | Count | How we got it | Actual |
| --- | --- | --- | --- |
| Event 2 teams on the day | ~31 | From Event 2 |  |
| Event 2 teams that register again | ~20 | About 65% come back (they already know the campus and the format) |  |
| New teams from Patna colleges and Amity | ~20 | About 2 new teams from each of the 9 colleges + Amity |  |
| Teams registered | ~40 | 20 + 20 |  |
| Teams on the day | 30–32 | About 80% attend after confirmation calls |  |
| Students on the day | 110–120 | 31 teams × 3.6 |  |
| Seats needed | ~150 | 115 students + ~35 judges, mentors and volunteers – check the venue |  |
| Teams that submit a prototype | 26–28 | About 85% of teams on the day |  |
| Teams that qualify for the final | 20 | About the top 75% of the 26–28 submissions |  |
| Companies | 6–8 | 5–6 from Event 2 + 1–2 new |  |
| Interviews | 10–15 | 6–8 companies × about 2 each |  |
| Offers | 2–4 | About 1 in 4 interviews |  |

# 7. Feasible targets for management

| Measure | Feasible target | Actual |
| --- | --- | --- |
| Teams registered / on the day | 40 / 30–32 |  |
| Students on the day | 110–120 |  |
| Teams submitting a prototype | 26–28 |  |
| Teams qualifying for the final | 20 |  |
| Companies | 6–8 |  |
| Interviews / offers | 10–15 / 2–4 |  |
| Feedback score (out of 5) | 4+ |  |

# 8. To confirm before announcing

- Mid-term dates and Holi 2027 date

- Venue seats with power and Wi-Fi for ~150 people

- Approval for the event to end at 10 PM, with transport

Budget: to be discussed later.