Event 1 – Get Hire-Ready Day

Working plan  •  Amity University Patna  •  Sat 28 Nov 2026  •  Draft 1 (11 Oct 2026)

# 1. At a glance

| Item | Plan |
| --- | --- |
| Name (working) | Get Hire-Ready Day – Code & Idea Contest |
| Date | Saturday 28 Nov 2026, 9:30 AM – 5:30 PM (fallback: Sat 16 or 23 Jan 2027 if exams clash) |
| Venue | Amity Patna – 2 computer labs (coding), 1 seminar hall (talks, pitches), 2–3 rooms (CV clinic, mock interviews) |
| Who can join | All Amity Patna students, all years and departments; solo for coding, teams of 2–4 for idea pitch |
| The big hook | A hiring outcome on day one: top 5 get internship interviews with partner companies; every participant gets a CV review |
| Other hooks | Co-hosted with GeeksforGeeks or Unstop (certificates, reach) • beginner track • one well-known speaker |
| Targets | 100+ registrations • 80+ attend • 2–3 companies • 5 internship interviews • 1 speaker |
| Budget | ₹10,000–15,000 (see section 7) |
| Why it matters | First proof for management: students come, companies engage, the team can deliver. Results sheet unlocks Event 2. |

# 2. What participants get

- CV review by HR people or alumni (everyone who attends)

- Internship interviews with partner companies (top 5)

- Certificates – participation for all, merit for winners (co-branded with GfG/Unstop if confirmed)

- Talk by a well-known speaker; small prizes and goodies for winners

- Mock interviews (first 30 to sign up on the day)

# 3. Tracks

| Track | Who | Format | Judged on |
| --- | --- | --- | --- |
| A. Beginner coding | 1st–2nd year, non-CSE | 90 min, 5–6 easy problems on GfG/Unstop/HackerRank | Problems solved, time |
| B. Advanced coding | 2nd year and above | 90 min, 4–5 medium/hard problems | Problems solved, time |
| C. Idea pitch | Teams of 2–4, any year | 3–5 slides on one of 3 problem statements; 5 min pitch + 2 min Q&A | Problem fit 25 • idea 25 • feasibility 25 • pitch 25 |

Idea pitch problem statements: 3, from faculty or a partner company (e.g. campus attendance, local shop digital payments, crop price alerts for farmers). Top 5 overall = top 2 coders (A+B) + top 3 pitch teams, or as agreed with companies.

# 4. Agenda – Sat 28 Nov 2026

| Time | What | Where | Owner |
| --- | --- | --- | --- |
| 8:30 | Volunteers and team arrive; labs and Wi-Fi checked | All rooms | Logistics lead |
| 9:00 | Check-in, ID cards, CV upload check | Entrance | Registration desk |
| 9:30 | Opening: welcome, rules, partner companies introduced | Seminar hall | Faculty convener + emcee |
| 10:00–11:30 | Coding rounds A and B | Labs 1 and 2 | Technical lead |
| 10:00–11:30 | Idea teams prepare (mentors available) | Seminar hall | Pitch lead |
| 11:45–12:30 | Speaker talk: "What companies look for in freshers" | Seminar hall | Speaker host |
| 12:30–13:15 | Lunch / snacks | Cafeteria | Hospitality |
| 13:15–15:00 | Idea pitches (5 + 2 min per team) | Seminar hall | Pitch lead + judges |
| 13:15–16:00 | CV clinic and mock interviews (in parallel) | Rooms 1–3 | T&P officer + HR/alumni |
| 15:00–15:45 | Coding results checked; judges finalise | Jury room | Jury head |
| 16:00–16:45 | Results and prizes; top 5 announced; interview slots shared | Seminar hall | Chief guest + companies |
| 16:45–17:15 | Photos, feedback form (QR code), networking with companies | Seminar hall | Media + T&P |
| 17:30 | Close; team debrief | — | Core team |

# 5. Partners to line up

| Partner | Ask | Give in return | Target count |
| --- | --- | --- | --- |
| Hiring companies (alumni employers, Patna IT firms, Bihar startups) | Send 1 HR or tech person; interview top 5 within 2 weeks; 1 judge | Logo, stage mention, CVs of all participants, first look at talent | 2–3 |
| GeeksforGeeks or Unstop | Co-host: free contest platform/listing, co-branded certificates, promotion | Logo, student sign-ups on their platform | 1 |
| Alumni / HR volunteers | CV review and mock interviews (2–3 hours) | Certificate of appreciation, stage thanks | 5–8 |
| Speaker | 30–45 min talk on getting hired | Travel/stay (if outside Patna), memento | 1 |

# 6. Team

| Role | People | Main jobs | Name |
| --- | --- | --- | --- |
| Faculty convener | 1 | Approval, faculty judges, final calls |  |
| T&P officer | 1 | Company contacts, CV clinic, interview follow-up |  |
| Student lead | 1 | Runs the team, daily check-ins, timeline |  |
| Company & partner relations | 2 | Companies, GfG/Unstop, alumni, speaker |  |
| Technical lead | 2 | Contest platform, problems, labs, scoring |  |
| Marketing | 2 | Posters, reels, class ambassadors, WhatsApp |  |
| Logistics & hospitality | 3 | Rooms, food, certificates, registration desk |  |
| Volunteers (on the day) | 8–10 | Desk, labs, guiding guests, photos |  |

# 7. Budget (estimate)

| Item | Amount (₹) | Notes |
| --- | --- | --- |
| Snacks, lunch boxes and tea (100–120 people) | 5,000–7,000 | Ask canteen for a bulk rate |
| Prizes and goodies for winners | 2,000–3,000 | Or vouchers/swag from GfG/Unstop/companies |
| Certificates and printing (posters, ID cards) | 1,500–2,000 | E-certificates save cost |
| Speaker memento / travel | 1,000–2,000 | Lower if the speaker is local or online |
| Miscellaneous (stationery, banners) | 500–1,000 |  |
| Total | 10,000–15,000 | Target ₹5,000+ from a local sponsor |

# 8. Week-by-week task list

| Week of | Tasks | Owner | Status |
| --- | --- | --- | --- |
| 12 Oct | Send approval note to management (section 11) • confirm date vs exam calendar and Chhath (around 15 Nov) • book labs and hall | Faculty convener, student lead |  |
| 19 Oct | Form team • list 15 companies and 15 alumni to contact • email GfG and Unstop campus teams • shortlist 3 speakers | Partner relations, T&P |  |
| 26 Oct | Send company and alumni invites • pick contest platform • draft 3 idea problem statements • design poster | Partner relations, technical, marketing |  |
| 2 Nov | Registration opens (form with CV upload) • class ambassadors in every section • first poster and reel • speaker confirmed | Marketing, technical |  |
| 9 Nov | Follow up companies (target 2–3 confirmed) • prepare coding problems • Diwali week – lighter promotion | Partner relations, technical |  |
| 16 Nov | Announce companies and speaker (big promotion push) • registration milestone post (50+) • order food | Marketing, hospitality |  |
| 23 Nov | Registration closes Wed 25 Nov • test labs and platform • print certificates • brief judges and HR volunteers • volunteer briefing | All leads |  |
| 28 Nov | EVENT DAY | Everyone |  |
| 30 Nov | Send thank-yous, CV packs to companies, certificates • collect feedback • fix interview dates for top 5 | T&P, partner relations |  |
| 7 Dec | Results sheet to management (section 10) + request approval for Event 2 | Faculty convener, student lead |  |

# 9. Promotion plan

- Main message: "Get hired, not just certified – top 5 get internship interviews."

- Class ambassadors: one per section; they share the link in class WhatsApp groups and collect sign-ups.

- Instagram: 3 reels (announcement, companies and speaker reveal, countdown) + milestone posts (50, 100 registrations).

- Posters at entrance, canteen, labs, hostels; announcement in classes by faculty.

- Beginner track called out clearly so 1st-years and non-CSE students sign up.

## Registration form fields

- Name, enrolment number, course, year, phone, email

- Track (beginner coding / advanced coding / idea pitch) and team details for pitch

- CV upload (PDF) – needed for the CV clinic and the company CV pack

- Consent to share CV with partner companies

- Want a mock interview? (yes/no)

# 10. Results sheet for management (fill after the event)

| Measure | Target | Actual |
| --- | --- | --- |
| Registrations | 100+ |  |
| Attended | 80+ |  |
| Departments represented | 4+ |  |
| Companies involved | 2–3 |  |
| Internship interviews given | 5 |  |
| CVs reviewed / mock interviews done | 80 / 30 |  |
| Total cost and cost per participant | ₹10–15k / about ₹150 |  |
| Sponsor money or in-kind support | ₹5,000+ |  |
| Feedback score (out of 5) | 4+ |  |
| Social media reach | 5,000+ views |  |

Add: photos, winners, 2–3 quotes from companies and students, what we change, and the request for Event 2 (Campus Hackathon, Sat 20 Feb 2027).

# 11. Message templates

## Approval note to management

Subject: Approval request – "Get Hire-Ready Day" (Sat 28 Nov 2026)

We propose a one-day coding and idea contest for all Amity Patna students on Saturday 28 November 2026. Partner companies will review CVs and interview the top 5 participants for internships. Expected participation: 100+ students. Budget: ₹10,000–15,000, partly covered by sponsors. This is the first of five events leading to a Bihar-level hackathon aimed at strengthening our placement network. We request approval for the date, venue (2 labs, seminar hall, 3 rooms) and budget.

## Invite to companies

Subject: Invitation – meet Amity Patna's top student talent on 28 Nov

Dear [Name], Amity University Patna is hosting "Get Hire-Ready Day", a coding and idea contest, on Saturday 28 November 2026. We would be glad to have [Company] join as a hiring partner: send one HR or technical person to judge and review CVs, and interview our top 5 participants for internships. You will receive the CVs of all participants and visibility at the event. Could we schedule a short call this week? Regards, [Name, role, phone]

## Message to GeeksforGeeks / Unstop

Hello, we are organising a coding and idea contest for 100+ students at Amity University Patna on 28 Nov 2026. We would like to host it on your platform and co-brand certificates. Could you share your campus partnership options? Regards, [Name]

## Announcement to students

Get hired, not just certified! Get Hire-Ready Day – Sat 28 Nov. Coding (beginner and advanced) + idea pitch. Free CV review for everyone, internship interviews for the top 5, talk by [Speaker]. Register by 25 Nov: [link]

# 12. Risks and backups

- Exam clash – check the calendar this week; fallback Sat 16 or 23 Jan 2027.

- Companies not confirmed – start with alumni employers; even 1 company + 5 alumni HR volunteers is enough for year one.

- Low sign-ups – ambassador push in week of 16 Nov; faculty announcements; make the CV review the headline.

- Platform or Wi-Fi failure – test 3 days before; keep offline problem sheets as backup.

- Speaker drops out – keep a second speaker or an online talk ready.