## Dashboard
Event 1 – Get Hire-Ready Day
Amity University Patna • Sat 28 Nov 2026 • Tracker workbook (updates automatically from the other tabs)
Event date |  |  | Change here if the date moves
Days to go
TASKS | Done | Total
Tasks done
Tasks progress
Tasks overdue (not done, due date passed) |  |  | Check the Tasks tab
PARTNERS | Confirmed | Target
Hiring companies confirmed |  | 3 | Target 2–3
Platform partner confirmed (GfG / Unstop) |  | 1
Alumni / HR volunteers confirmed |  | 6 | Target 5–8
Speaker confirmed |  | 1
REGISTRATIONS | Actual | Target
Total registrations |  | 100
Registrations vs target
BUDGET (₹) | Amount
Planned (max)
Spent so far
Sponsor money received |  |  | Target ₹5,000+
Net cost to Amity
How to use: fill the yellow cells on each tab. Blue text = typed input, black = formula. Status columns have drop-down lists. Grey rows are examples – overwrite or delete them.

## Tasks
Tasks
Week-by-week task list from the Event 1 plan. Update Owner, Due date and Status.
Red due date = overdue. Add new tasks at the bottom.
Week of | Task | Area | Owner | Due date | Status | Notes
2026-10-12 | Send approval note to management | Approvals |  | 2026-10-16 | Not started
2026-10-12 | Check 28 Nov against exam calendar and Chhath (around 15 Nov) | Approvals |  | 2026-10-14 | Not started
2026-10-12 | Book 2 labs, seminar hall and 3 rooms | Logistics |  | 2026-10-16 | Not started
2026-10-19 | Form core team and fill the Team tab | Team |  | 2026-10-21 | Not started
2026-10-19 | List 15 companies and 15 alumni in the Partners tab | Partners |  | 2026-10-23 | Not started
2026-10-19 | Email GeeksforGeeks and Unstop campus teams | Partners |  | 2026-10-22 | Not started
2026-10-19 | Shortlist 3 speakers | Partners |  | 2026-10-23 | Not started
2026-10-26 | Send invites to companies and alumni | Partners |  | 2026-10-28 | Not started
2026-10-26 | Pick contest platform | Technical |  | 2026-10-30 | Not started
2026-10-26 | Draft 3 idea-pitch problem statements | Technical |  | 2026-10-30 | Not started
2026-10-26 | Design poster and registration form (with CV upload) | Marketing |  | 2026-10-30 | Not started
2026-11-02 | Open registration | Marketing |  | 2026-11-02 | Not started
2026-11-02 | Appoint class ambassadors (one per section) | Marketing |  | 2026-11-04 | Not started
2026-11-02 | First poster and reel out | Marketing |  | 2026-11-04 | Not started
2026-11-02 | Confirm speaker | Partners |  | 2026-11-06 | Not started
2026-11-09 | Follow up companies – target 2–3 confirmed | Partners |  | 2026-11-13 | Not started
2026-11-09 | Prepare coding problems (beginner + advanced) | Technical |  | 2026-11-13 | Not started
2026-11-16 | Announce companies and speaker (big promotion push) | Marketing |  | 2026-11-17 | Not started
2026-11-16 | Post registration milestone (50+) | Marketing |  | 2026-11-18 | Not started
2026-11-16 | Order food and refreshments | Logistics |  | 2026-11-20 | Not started
2026-11-23 | Close registration (Wed 25 Nov) | Marketing |  | 2026-11-25 | Not started
2026-11-23 | Test labs, Wi-Fi and contest platform | Technical |  | 2026-11-25 | Not started
2026-11-23 | Print certificates, ID cards, banners | Logistics |  | 2026-11-26 | Not started
2026-11-23 | Brief judges and HR/alumni volunteers | Partners |  | 2026-11-26 | Not started
2026-11-23 | Volunteer briefing | Team |  | 2026-11-27 | Not started
2026-11-28 | EVENT DAY | Everyone |  | 2026-11-28 | Not started
2026-11-30 | Send thank-yous and certificates | Partners |  | 2026-12-01 | Not started
2026-11-30 | Send CV packs to companies | Partners |  | 2026-12-02 | Not started
2026-11-30 | Collect feedback; fix interview dates for top 5 | Partners |  | 2026-12-04 | Not started
2026-12-07 | Fill Results tab; send results sheet + Event 2 request to management | Approvals |  | 2026-12-09 | Not started

## Team
Team
Fill names and contacts. Grey row = example.
Role | People needed | Name(s) | Phone | Email | Main jobs
Example: Marketing | 2 | Riya Kumari, Aman Singh | 98XXXXXXXX | riya@example.com | Posters, reels, ambassadors
Faculty convener | 1 |  |  |  | Approval, faculty judges, final calls
T&P officer | 1 |  |  |  | Company contacts, CV clinic, interview follow-up
Student lead | 1 |  |  |  | Runs the team, daily check-ins, timeline
Company & partner relations | 2 |  |  |  | Companies, GfG/Unstop, alumni, speaker
Technical lead | 2 |  |  |  | Contest platform, problems, labs, scoring
Marketing | 2 |  |  |  | Posters, reels, class ambassadors, WhatsApp
Logistics & hospitality | 3 |  |  |  | Rooms, food, certificates, registration desk
Volunteers (event day) | 10 |  |  |  | Desk, labs, guiding guests, photos
Total people

## Partners
Partners & outreach
Companies, platform, alumni/HR volunteers and speaker. Status drives the Dashboard counts.
Type | Organisation / person | Contact person | Phone / email | What we ask | Date contacted | Follow-up date | Owner | Status | Notes
Example | ABC Technologies, Patna | HR Manager | hr@example.com | HR judge + interview top 5 | 2026-10-28 | 2026-11-04 | Aman | Interested | Call back Monday
Platform | GeeksforGeeks | Campus team |  | Co-host: platform, co-branded certificates, promotion |  |  |  | Not contacted
Platform | Unstop | Campus team |  | Co-host: listing, certificates, promotion |  |  |  | Not contacted
Company |  |  |  | HR/tech judge; interview top 5; CV pack |  |  |  | Not contacted
Company |  |  |  | HR/tech judge; interview top 5; CV pack |  |  |  | Not contacted
Company |  |  |  | HR/tech judge; interview top 5; CV pack |  |  |  | Not contacted
Company |  |  |  | HR/tech judge; interview top 5; CV pack |  |  |  | Not contacted
Company |  |  |  | HR/tech judge; interview top 5; CV pack |  |  |  | Not contacted
Company |  |  |  | HR/tech judge; interview top 5; CV pack |  |  |  | Not contacted
Company |  |  |  | HR/tech judge; interview top 5; CV pack |  |  |  | Not contacted
Company |  |  |  | HR/tech judge; interview top 5; CV pack |  |  |  | Not contacted
Company |  |  |  | HR/tech judge; interview top 5; CV pack |  |  |  | Not contacted
Company |  |  |  | HR/tech judge; interview top 5; CV pack |  |  |  | Not contacted
Company |  |  |  | HR/tech judge; interview top 5; CV pack |  |  |  | Not contacted
Company |  |  |  | HR/tech judge; interview top 5; CV pack |  |  |  | Not contacted
Company |  |  |  | HR/tech judge; interview top 5; CV pack |  |  |  | Not contacted
Company |  |  |  | HR/tech judge; interview top 5; CV pack |  |  |  | Not contacted
Company |  |  |  | HR/tech judge; interview top 5; CV pack |  |  |  | Not contacted
Alumni / HR |  |  |  | CV review + mock interviews (2–3 h) |  |  |  | Not contacted
Alumni / HR |  |  |  | CV review + mock interviews (2–3 h) |  |  |  | Not contacted
Alumni / HR |  |  |  | CV review + mock interviews (2–3 h) |  |  |  | Not contacted
Alumni / HR |  |  |  | CV review + mock interviews (2–3 h) |  |  |  | Not contacted
Alumni / HR |  |  |  | CV review + mock interviews (2–3 h) |  |  |  | Not contacted
Alumni / HR |  |  |  | CV review + mock interviews (2–3 h) |  |  |  | Not contacted
Alumni / HR |  |  |  | CV review + mock interviews (2–3 h) |  |  |  | Not contacted
Alumni / HR |  |  |  | CV review + mock interviews (2–3 h) |  |  |  | Not contacted
Alumni / HR |  |  |  | CV review + mock interviews (2–3 h) |  |  |  | Not contacted
Alumni / HR |  |  |  | CV review + mock interviews (2–3 h) |  |  |  | Not contacted
Speaker |  |  |  | 30–45 min talk: what companies look for in freshers |  |  |  | Not contacted
Speaker |  |  |  | 30–45 min talk: what companies look for in freshers |  |  |  | Not contacted
Speaker |  |  |  | 30–45 min talk: what companies look for in freshers |  |  |  | Not contacted

## Budget
Budget (₹)
Plan ranges are estimates from the Event 1 plan. Enter actual spend as bills come in.
Item | Planned min | Planned max | Actual spent | Paid by | Notes
Snacks, lunch boxes and tea (100–120 people) | 5000 | 7000 |  |  | Ask canteen for bulk rate
Prizes and goodies | 2000 | 3000 |  |  | Or swag from GfG/Unstop/companies
Certificates and printing (posters, ID cards) | 1500 | 2000 |  |  | E-certificates save cost
Speaker memento / travel | 1000 | 2000 |  |  | Lower if speaker is local or online
Miscellaneous (stationery, banners) | 500 | 1000
(add item)
Total
SPONSOR INCOME
Sponsor | Type (cash / in kind) | Amount received (₹)
Total sponsor money
Source of planned figures: Event 1 plan (Event1_Hire_Ready_Day_Plan.docx, section 7) – estimates, replace with real quotes.

## Registrations
Registrations
Copy counts from the registration form (Google Form / platform) each day, by department and track.
Department | Beginner coding | Advanced coding | Idea pitch (people) | Attended (event day) | Mock interview requests | CVs uploaded | Total registered
CSE / IT
BCA / MCA
ECE / EEE
Mechanical / Civil
Management (BBA/MBA)
Commerce / Other
Sciences
Other
Total
DAILY LOG (for milestone posts)
Date | Total registrations | Note
2026-11-03 | 12 | Example – day 2 after opening

## Results
Results sheet for management
Fill after the event. Targets from the Event 1 plan. Linked cells fill automatically.
Measure | Target | Actual | Met? | Notes
Registrations | 100
Attended | 80
Departments represented | 4
Companies involved | 2
Internship interviews given | 5
CVs reviewed | 80
Mock interviews done | 30
Sponsor money / in-kind (₹) | 5000
Feedback score (out of 5) | 4
Social media views | 5000
Total cost (₹) |  |  |  | From Budget tab
Cost per participant (₹) |  |  |  | Total cost ÷ attended
Also attach: photos, winners, 2–3 quotes from companies and students, what we change, and the request for Event 2 (Campus Hackathon, Sat 20 Feb 2027).