Amity Patna – Bihar-Level Hackathon Plan

Placement-led event ladder  •  Draft 6  •  11 Oct 2026

# 1. Goal

Build Amity Patna's image for placements: "Amity Patna is where Bihar's companies find talent."

The final goal is a Bihar-level hackathon where companies give real problem statements, students solve them, and company experts judge together with our faculty – and then recruit from it. To get management approval for it, we run a ladder of smaller events. Each one is bigger than the last, and after each one we show management the results.

# 2. Placement principles (apply to every event)

- Invite companies that hire freshers and interns, not only sponsors: IT and services firms, Bihar startups, banks, PSU plants.

- Company judges are future recruiters: ask each company to send an HR person or hiring manager along with a technical expert.

- Every event ends with a hiring step: agree in advance that companies interview the top teams or offer internships to winners.

- Collect CVs at registration; after the event, send each company a CV pack of the teams who worked on its problem.

- The Training & Placement (T&P) officer is on the team from Event 1; every company contact goes into the placement cell's list.

# 3. Event ladder – small to Bihar level

| # | Event | When | Scale | Length | Problem statements from | Budget (estimate) | What it proves to management |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Get Hire-Ready Day (Code & Idea Contest) | Sat 28 Nov 2026 (or Jan 2027 if exams clash) | Whole campus, 100+ students | 1 day | Faculty + 1 company | ₹10,000–15,000 | Students show up; companies engage; the team can run an event |
| 2 | Amity Patna Campus Hackathon | Sat 20 Feb 2027 | 200+ participants, 1,000+ campus visitors | 12 hours | Bihar govt office + 1–2 companies | ₹60,000–1 lakh | Campus-wide buzz; government and companies engage; local press |
| 3 | Patna Inter-College Hackathon | Sat–Sun 10–11 Apr 2027 | 5–8 Patna colleges, 200–250 students | 24 hours | 4–6 companies | ₹1–1.5 lakh | Other colleges come; companies send judges; Amity known in Patna |
| 4 | Bihar Online Ideathon (qualifier) | 17 Jul–7 Aug 2027 | All of Bihar, 500+ registrations | 3 weeks online | 10–15 companies | ₹50,000–1 lakh | Statewide reach at low cost; picks finalists for Event 5 |
| 5 | Bihar-Level Hackathon – FINAL GOAL | Sat–Sun 18–19 Sep 2027 (fallback: 20–21 Nov 2027) | 60–80 finalist teams from across Bihar | 30 hours | 15–25 Bihar companies; judged by companies + faculty | ₹4–8 lakh | The goal event |

Each event roughly doubles the last in participants, colleges and companies. Event 4 is the qualifier, so Event 5 starts with a confirmed list of strong teams. Dates avoid the crowded Jan–Feb fest season for outside events and use Bihar's open slots; verify Amity Patna exams and the 2027 Bihar holiday list before announcing.

# 4. Event details

## Event 1 – Get Hire-Ready Day (Sat 28 Nov 2026)

- Big hook (Flipkart GRiD / TCS CodeVita model): top 5 get internship interviews with 2–3 partner companies; every participant gets a CV review.

- Other hooks: co-hosted with GeeksforGeeks or Unstop (Hash Code-style brand pull); beginner track (Hack This Fall model); one well-known speaker.

- Format: beginner coding, advanced coding, idea pitch on 3 problem statements; CV clinic and mock interviews in parallel.

- Full working plan: separate file Event1_Hire_Ready_Day_Plan.docx.

## Event 2 – Amity Patna Campus Hackathon (Sat 20 Feb 2027)

- Format: 12 hours, teams of 2–4, open to all Amity Patna departments.

- Big hook (Smart India Hackathon model): 2–3 problem statements from a Bihar government office (Patna district administration, Bihar Police cyber cell or Patna Smart City) + 1–2 companies; the officer gives the prizes – brings local press.

- Headline chief guest (Celesta model): ISRO/DRDO scientist, senior government officer or armed forces officer.

- Spectator show (Techfest Robowars / Amity Lucknow esports model): robot battle or drone demo + esports zone open to the whole campus.

- Positioning (PennApps model): e.g. "Patna's first campus hackathon with government problem statements" – only if verified.

- Placement step: top 3 teams get internship interviews with the partner companies.

- Agenda: 7:00 check-in • 7:30 problem statements • 8:00–20:00 hacking • 11:30 chief guest keynote + robot/drone show • 20:00 judging • 21:15 top-6 pitches • 21:45 prizes.

- Full working plan: separate file Event2_Campus_Hackathon_Plan.docx.

## Event 3 – Patna Inter-College Hackathon (Sat–Sun 10–11 Apr 2027)

- Format: 24 hours, 5–8 Patna colleges invited (NIT Patna, BIT Patna, Patna Women's College, NSIT, Patna University colleges, others).

- Problem statements and judges from 4–6 companies, plus faculty.

- Placement step: hiring desk at the event; winners get internship or pre-placement interview offers; CV packs to companies.

- Agenda: Day 1 – 10:00 opening, statements • 11:00 hacking • 16:00 and 22:00 mentor rounds. Day 2 – 11:00 submissions • 11:30 judging • 14:00 top-5 pitches • 15:30 results and hiring desk.

## Event 4 – Bihar Online Ideathon (17 Jul–7 Aug 2027)

- Format: online on Unstop/Devfolio; teams submit a 5-slide idea for one company problem statement.

- Problem statements from 10–15 companies; faculty screen first, each company picks its top teams.

- Placement step: CV pack to every company; companies can contact strong teams directly.

- Output: 60–80 finalist teams for Event 5.

## Event 5 – Bihar-Level Hackathon, FINAL GOAL (Sat–Sun 18–19 Sep 2027)

- Format: 30 hours in person at Amity Patna; finalists from Event 4.

- Problem statements from 15–25 Bihar companies; panels of company judges + faculty (rules in section 6).

- Placement step: on-the-spot internship and job offers; companies invited to Amity Patna's campus recruitment season.

- Sat: 8:30 check-in • 9:30 opening with company leaders • 10:30 hacking starts • 15:00 company stalls and hiring desk open • 17:00 and 23:00 mentor rounds • overnight hacking.

- Sun: 9:00 final mentor round • 16:30 submissions close (30 hours) • 16:30–18:30 judging per problem statement • 18:30 top-10 pitches • 19:30 prizes, offers announced, close.

# 5. What we report to management after each event

| Measure | E1 | E2 | E3 | E4 | E5 |
| --- | --- | --- | --- | --- | --- |
| Registrations | 100+ | 200+ | 250 | 500+ | 300+ applicants → 80 teams |
| Colleges | 1 | 1 | 5–8 | 30+ | 30+ |
| Companies that took part | 1–2 | 2–3 | 4–6 | 10–15 | 15–25 |
| Internship / job interviews given | — | 3–5 | 10+ | 20+ | 50+ |
| Offers made (internships, jobs, fast-tracks) | — | 1–3 | 5+ | 10+ | 25+ |
| New companies that later come for campus placements | — | 1 | 2–3 | 5 | 10+ |
| Amity Patna students in the top 10 | track | track | track | track | track |
| Sponsor money raised | ₹5,000+ | ₹30,000+ | ₹50,000+ | ₹1 lakh+ | ₹4 lakh+ |
| Satisfaction (participants and companies) | 4/5 | 4/5 | 4/5 | — | 4.5/5 |
| Media / social reach | campus | campus | local news | state | state news |

The most important row for management: new companies that later come for campus placements. Targets are starting points – adjust them after Event 1's real numbers.

## One-page results sheet (after every event)

- Numbers from the table above, actual vs target

- Photos, winning projects, quotes from company judges

- Companies met and their hiring interest (handed to the placement cell)

- Cost per participant and money raised

- What went wrong and what we change

- "What we need for the next event": budget, venue, approvals – the approval request each time

# 6. Final hackathon format – company problem statements

## What companies give and get

| Partner level | Company gives | Company gets |
| --- | --- | --- |
| Problem Partner (free) | 1–2 problem statements, 1 mentor, 1–2 judges (incl. HR / hiring manager) | Working prototypes, first pick of talent, CV pack, logo on all material |
| Prize Partner | Problem statement + prize for it (₹25k–1 lakh) | Above + named prize, stall, interviews/offers to winners |
| Title / Associate Sponsor | Funding for the event | Naming rights, keynote slot, branding across the ladder |

## Problem statement template (send to every company)

- Company, contact, domain (agri, energy, health, govt, manufacturing, finance, open)

- Title and background: the problem today and who faces it

- Expected outcome and what "solved" looks like

- Data or resources shared (sample data, site visit, API) and any NDA needed

- Company-specific success criteria; prize (if any); internship/hiring interest

- IP preference: default is students own their work; the company gets first right to license it

## Judging

| Criterion | Marks |
| --- | --- |
| Understanding of the company's problem | 15 |
| Innovation and originality | 20 |
| Working prototype / technical execution | 25 |
| Feasibility, cost and scalability for the company | 20 |
| Impact (for the company and for Bihar) | 10 |
| Presentation and Q&A | 10 |
| Total | 100 |

- Panel per problem statement: 1–2 company judges + 1 faculty judge. Final score = company 60% + faculty 40%.

- Conflict of interest: faculty never judge teams from their own college or teams they mentored; Amity Patna teams are judged by outside faculty or company judges only.

- Scores go into a shared sheet in real time; a jury head checks for big gaps between panels before results.

- Test this rubric from Event 2 onwards so it is proven by Event 5.

# 7. Companies to approach (willingness and hiring not yet checked)

| Group | Examples | Likely problem areas | Bring in from |
| --- | --- | --- | --- |
| Alumni and local firms | Amity alumni employers, Patna IT and service companies | Software, operations | Event 1–2 |
| Bihar startups | DeHaat (agritech), Husk Power Systems (rural energy), Agrix, Sattuz, iMithila, Medishala | Supply chain, rural power, e-commerce, health access | Event 2–3 |
| PSUs and industry in Bihar | IOCL Barauni Refinery, NTPC (Barh, Barauni), HURL Barauni, Sudha Dairy (COMFED), Varun Beverages Barauni, Prince Pipes | Safety, maintenance, energy efficiency, quality, logistics | Event 3–5 |
| Government | Bihar IT, Agriculture, Health departments; Bihar Police EOU; Bihar startup cell | Citizen services, cyber fraud, crop advisory, flood response | Event 4–5 |
| Banks and services | SBI, regional rural banks, hospitals, logistics firms | Fraud detection, financial inclusion, scheduling | Event 3–5 |
| Hiring platforms | Unstop, Devfolio, GeeksforGeeks | Platform + hiring reach | Event 3–5 |

# 8. Budget and money

| Event | Budget (estimate) | Main costs | Sponsor target |
| --- | --- | --- | --- |
| 1. Get Hire-Ready Day | ₹10,000–15,000 | Food, certificates, prizes, speaker | ₹5,000+ |
| 2. Campus hackathon | ₹60,000–1 lakh | Food (12 h), prizes, chief guest, robot/drone demo, esports zone | ₹30,000+ |
| 3. Patna inter-college | ₹1–1.5 lakh | Food (24 h), prizes, Wi-Fi/power, outside-team hospitality | ₹50,000+ |
| 4. Bihar online ideathon | ₹50,000–1 lakh | Platform fees, promotion, campus ambassadors | ₹1 lakh+ |
| 5. Bihar-level hackathon | ₹4–8 lakh | Prizes, food (30 h), finalist travel support, company hospitality, stage and AV | ₹4 lakh+ |
| Total (Nov 2026 – Sep 2027) | ₹6.9–11.7 lakh |  | ₹5.9 lakh+ |

Estimates only – replace with real quotes. Income: sponsors, prize partners, Amity support. Companies may fund prizes through CSR – their CSR team must confirm eligibility.

## Budget breakdown by event (brief)

| Event | Food & refreshments | Prizes & goodies | Guests / speakers | Venue, tech & show | Promotion & printing | Total (₹) |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Get Hire-Ready Day | 5–7k | 2–3k | 1–2k | — (own labs) | 2–3k | 10–15k |
| 2. Campus Hackathon | 20–30k (12 h, 200 people) | 15–25k | 10–15k (chief guest) | 10–20k (robot/drone demo, esports zone, sound) | 5–10k | 60k–1 lakh |
| 3. Patna Inter-College | 40–55k (24 h, 250 people) | 30–40k | 10–15k | 10–20k (Wi-Fi, power backup) | 10–20k | 1–1.5 lakh |
| 4. Bihar Online Ideathon | — | 10–20k | — | 15–30k (platform fees) | 25–50k (ambassadors, ads) | 50k–1 lakh |
| 5. Bihar-Level Hackathon | 1–1.5 lakh (30 h, 300+ people) | 1.5–3 lakh | 50k–1 lakh (company hospitality, finalist travel) | 50k–1.5 lakh (stage, AV, Wi-Fi) | 50k–1 lakh | 4–8 lakh |

Totals are approximate; each column is a range. For every event, aim to cover at least half the cost through sponsors and in-kind support (food, swag, platform, prizes).

# 9. Month-by-month timeline

| Month | Main work |
| --- | --- |
| Oct 2026 | Approval for Event 1; form core team (with T&P officer); company target list |
| Nov 2026 | EVENT 1 (28 Nov) • results sheet to management |
| Dec 2026 – Jan 2027 | Approval for Event 2; sign 1–2 local companies; set up registration and CV collection |
| Feb 2027 | EVENT 2 (20 Feb) • results sheet • internship interviews for top teams |
| Mar 2027 | Approval for Event 3; invite Patna colleges; sign 4–6 companies |
| Apr 2027 | EVENT 3 (10–11 Apr) • results sheet • hiring follow-up with companies |
| May–Jun 2027 | Approval for Events 4–5; sign 10–15 companies; collect problem statements; book platform |
| Jul–Aug 2027 | EVENT 4 online (17 Jul–7 Aug) • campus ambassadors across Bihar • finalists selected • confirm 15–25 companies and judges |
| Sep 2027 | EVENT 5 (18–19 Sep) • offers announced |
| Oct 2027 | Final report to management; companies invited to the campus placement season |

# 10. Team

| Role | E1–E2 | E3 | E4–E5 |
| --- | --- | --- | --- |
| Faculty convener | 1 | 1 | 1–2 |
| T&P / placement officer | 1 | 1 | 1 + placement cell |
| Student lead | 1 | 1 | 1 + deputies |
| Company relations | 1–2 | 3 | 4–6 |
| Events / technical | 2–3 | 4 | 6–8 |
| Marketing & social media | 1–2 | 3 | 4–6 |
| Logistics & hospitality | 2–3 | 5 | 10–15 + volunteers |

# 11. Risks

- Low company interest early on – start with alumni employers and local firms; the Problem Partner level is free.

- Companies judge but don't hire – agree the hiring step (interviews/internships) in writing before each event.

- Low turnout from other colleges – visit colleges, use student ambassadors, free entry, certificates.

- Exams, festivals or elections clash – check calendars before announcing; keep fallback dates.

- Amity Patna students don't reach the top – run skill workshops between events.

- IP or data disputes – default IP policy and NDAs agreed before problem statements go out; Amity legal review.

# 12. After the final goal

- If Event 5 succeeds: make it yearly, and build a tech fest around the Grand Finale (Nov slot).

- Year 2 (2028): add companies from across India and open registration nationally.

# 13. Decisions needed now

- Approve Event 1 – Get Hire-Ready Day (28 Nov 2026, ₹10,000–15,000)

- Appoint faculty convener and confirm the T&P officer's role

- Form the core student team

- List the first 10 companies and alumni to approach

- Agree the results sheet format for management