Proposal: Two Patna Inter-College Events, Jan–Mar 2027

For management approval  •  Amity University Patna  •  12 Oct 2026

# 1. The proposal in brief

We propose two events open to every college in Patna, run at Amity Patna in the even semester. Their purpose is to make Amity Patna the place where Patna's students meet employers, which strengthens our placements and our name in the city.

|  | Event A – Code & Idea Day | Event B – Inter-College Hackathon |
| --- | --- | --- |
| When | Sat 16 Jan 2027 (online prelim Sun 10 Jan) – early in the 4th semester | Sat–Sun 27–28 Mar 2027 – after mid-terms |
| Format | 1 day: coding contest, idea pitch, CV clinic and mock interviews, hiring talk | 24-hour hackathon on problem statements set by companies; hiring desk |
| Who | Students of 15+ Patna colleges | Teams from 15+ Patna colleges |
| Scale | 400+ registrations, 200–250 on campus | 300 registrations, 60–75 teams on campus |
| Companies | 3–5 (judge, review CVs, interview top 10) | 5–8 (set problems, judge, interview and make offers) |
| Budget | ₹55,000–90,000 (sponsor target ₹25,000+) | ₹1.2–1.8 lakh (sponsor target ₹60,000+) |

Detailed working plans: Event_A_Code_and_Idea_Day_Plan.docx and Event_B_Inter_College_Hackathon_Plan.docx.

# 2. Why these two events, and why these dates

- Placements: every event ends with interviews or offers, and every company contact goes to the placement cell. Companies that meet students from 15+ colleges at Amity Patna are more likely to come to our campus recruitment.

- No Amity Patna presence in the city yet: only IIT Patna runs large tech fests in Patna (Celesta, Anwesha). An inter-college event series that focuses on hiring sets us apart.

- Jan 16: students are back in the new semester and not yet in exams; it comes before the late-January fest rush (Celesta, Elegante, Virasat).

- Mar 27–28: after mid-terms and Holi, and before end-semester preparation. Two months after Event A, so the same college network and companies can be used again.

- Step by step: Event A is low-risk (1 day, no overnight stay). Event B needs a separate approval after we report Event A's results.

# 3. How we will reach every Patna college

Each college hears about the events from people inside it, not only from posters. We build a 4-layer contact network in every college in Oct–Nov 2026 and use it for both events.

| Layer | In every college | How we get them | What they do |
| --- | --- | --- | --- |
| Institution | Principal / Director | Letter from our Director + visit by the faculty convener | Allows the notice; names a faculty coordinator |
| Faculty coordinator | 1 teacher (CSE/IT/BCA) | Named during the visit | Class announcements, notice board, travels with teams |
| Student ambassadors | 2 students (30+ in all) | Coding clubs, IEEE/GDG chapters, LinkedIn | Class WhatsApp groups, posters, info talks, team forming |
| Clubs and groups | Coding clubs, E-cells, NSS/NCC | Through ambassadors | Bring whole clubs as teams |

## Colleges to cover (15+)

| Group | Colleges |
| --- | --- |
| Engineering / tech | NIT Patna • IIT Patna (Bihta) • BIT Mesra Patna campus • NSIT Bihta • Maulana Azad College of Engineering & Technology |
| Patna University colleges | Patna Science College • Patna College • B.N. College • Magadh Mahila College • Patna Women's College |
| Other degree colleges (BCA/BBA) | A.N. College • College of Commerce, Arts & Science • St. Xavier's College of Management & Technology • J.D. Women's College • Arvind Mahila College |
| Management / design | Chandragupt Institute of Management Patna • NIFT Patna |

# 4. How we keep participants engaged (Oct 2026 – Apr 2027)

| Period | Engagement activity | Result we look for |
| --- | --- | --- |
| Oct – Nov 2026 | Visit 15+ colleges; faculty coordinators and 30+ ambassadors on board; companies invited | Every college has a coordinator and 2 ambassadors |
| 30 Nov – 9 Jan | Event A registration; 2 free online practice contests (13 Dec, 3 Jan); pitch webinar (6 Jan); weekly college-wise sign-up board | 400+ registrations from 15+ colleges |
| 10 – 16 Jan | Online prelim open to all → on-campus finals, idea pitches, CV clinic for every student who comes | 300+ take the prelim; 200–250 on campus |
| After Event A | Certificates and photos by college; top 10 interviews; all participants invited to Event B first | Interviews held; early Event B sign-ups |
| 8 Feb – 24 Mar | Event B registration; online team matching (20 Feb); company problem statements revealed (week of 22 Feb); briefings in March | 300 registrations; 60–75 teams |
| 27–28 Mar | 24 hours of building with company mentors; hiring desk; best college trophy | 80%+ teams submit a working prototype |
| After Event B | Interviews and offers followed up; all teams invited to the next statewide event | Offers made; companies invited to campus placements |

Each step has a number we check weekly (registrations by college, ambassador sign-ups, confirmations). If a college is behind, the outreach team visits it again.

# 5. Results we commit to

| Measure | Event A (16 Jan) | Event B (27–28 Mar) | Year total |
| --- | --- | --- | --- |
| Patna colleges that took part | 15+ | 15+ | 15+ (same network) |
| Students registered | 400+ | 300 | 500+ different students |
| Students on campus | 200–250 | 240+ | 400+ |
| Companies involved | 3–5 | 5–8 | 8–10 different companies |
| Internship / job interviews given | 10 | 15+ | 25+ |
| Offers made (internships, PPIs, fast-tracks) | track | 5+ | 5–10 |
| New companies that later come for campus placements | 1 | 2–3 | 3–5 |
| CVs reviewed / mock interviews (Event A) | 150 / 40 | — | 150 / 40 |
| Sponsor money and in-kind support | ₹25,000+ | ₹60,000+ | ₹85,000+ |
| Participant and company feedback (out of 5) | 4+ | 4+ | 4+ |
| Media | 2–3 local news mentions | 1–2 local news stories | 3+ stories; 40,000+ social views |

The most important row for management: new companies that later come to Amity Patna for campus placements. These targets are starting points; after Event A we will adjust Event B's targets using real numbers.

# 6. How we report results

- One-page results sheet within 10 days of each event (Event A: by 25 Jan; Event B: by 12 Apr): targets against actual numbers, photos, quotes from companies and visiting faculty, cost per participant, money raised, what went wrong, and what we will change.

- College-wise view: participants and winners from each college, to show how far the events reached across Patna.

- Company list for the placement cell: every company met, who came, and their hiring interest.

- Year report (April 2027): both events together, and a recommendation on whether to take the series to Bihar level in Jul–Sep 2027.

# 7. Budget and money

| Event | Budget (estimate) | Main costs | Sponsor target | Net from Amity (estimate) |
| --- | --- | --- | --- | --- |
| A – Code & Idea Day | ₹55,000–90,000 | Food for 250, prizes, best college trophy, college visits, printing | ₹25,000+ | ₹30,000–65,000 |
| B – Inter-College Hackathon | ₹1,20,000–1,80,000 | Food for 24 hours (300 people), prizes, Wi-Fi/power backup, rest rooms, travel help | ₹60,000+ | ₹60,000–1,20,000 |
| Total | ₹1.75–2.7 lakh |  | ₹85,000+ | ₹0.9–1.85 lakh |

Estimates only; real quotes come before each approval. Sponsors: Patna companies, banks, ed-tech/coaching firms, food partners; companies can fund named prizes. GeeksforGeeks/Unstop co-hosting can make the contest platform free.

# 8. Timeline

| Month | Main work |
| --- | --- |
| Oct 2026 | Approval for Event A • form the team (with T&P officer) • college contact sheet • start college visits |
| Nov 2026 | College visits finished (around Diwali 8 Nov and Chhath) • ambassadors on board • companies and speaker confirmed • registration opens 30 Nov |
| Dec 2026 | Exams – online engagement only (practice contest 13 Dec) • problems written and tested |
| Jan 2027 | Semester starts – main promotion push • prelim 10 Jan • EVENT A 16 Jan • results sheet and Event B approval request by 25 Jan |
| Feb 2027 | Event B registration opens 8 Feb • company problem statements published (week of 22 Feb) |
| Mar 2027 | Mid-terms – light touch • confirmations • EVENT B 27–28 Mar |
| Apr 2027 | Interviews and offers followed up • results sheet and year report by 12 Apr |

# 9. Team and main risks

| Team | People |
| --- | --- |
| Faculty convener | 1 |
| T&P / placement officer | 1 |
| Student lead + deputy | 2 |
| College outreach (visits, ambassadors) | 3–4 |
| Company relations | 2–3 |
| Technical, marketing, logistics | 8–12 |
| Volunteers on event days | 20 (Event A) • 30 (Event B) |

- Colleges slow to respond: the Director's letter and an in-person visit; ambassadors can sign students up while the college replies.

- Companies judge but do not hire: interview and offer numbers agreed in writing before each event; the T&P officer follows up within 2 weeks.

- Exam clashes: confirm each college's calendar during the visits. Fallback dates: Sat 30 Jan for Event A, Sat–Sun 3–4 Apr for Event B.

- Overnight stay for Event B: separate supervised rest rooms with a woman warden, consent forms, first aid and security. If overnight is not approved, Event B runs as a 12-hour hackathon.

# 10. Decisions needed now

- Approve Event A – Patna Inter-College Code & Idea Day (Sat 16 Jan 2027, budget ₹55,000–90,000), including entry of students from other colleges

- Approve in principle Event B – Patna Inter-College Hackathon (Sat–Sun 27–28 Mar 2027); final approval after the Event A results sheet

- Letters from the Director to the principals of 15+ Patna colleges

- Appoint the faculty convener and confirm the T&P officer's role

- Hold the venue: 3 labs, auditorium and 4 rooms on 16 Jan; main hall, labs and auditorium on 27–28 Mar